## Table D.1
Web Table D.1: Top 30 - Sustainment Products by expenditure, 2018-19
Product name | Product environment/ number | Budget estimate 2018-19 $m | Revised estimate 2018-19 $m | Actual expenditure 2018-19 $m | Variation $m | Portfolio Budget Statements 2018-19 | Portfolio Additional Estimates 2018-19 | Product update and explanation of variation 2018-19
|  |  | (a) | (b) | (b-a)
Air
F/A-18F Super Hornet Weapon System | CAF21 | 414.4326 | 435.8488 | 436.0687 | 0 | The RAAF 82 Wing operate fleets of F/A-18F Super Hornet and F/A-18G E/A-18G Growler Block II aircraft in support of air combat capability requirements. The Super Hornet achieved Final Operational Capability in December 2012. The Growler is on schedule to obtain Initial Operational Capability in July 2018. In-service support arrangements are through prime contracts with Boeing (platform stewardship), Raytheon (training support) and GE II (engine support). Through 2018-19, the spiral capability upgrades will continue on both Super Hornet and Growler aircraft, which include upgrades to aircraft hardware, software and the addition of new weapons. Following Initial Operating Capability, the focus for the Growler platform will shift towards Final Operational Capability in 2022. Growler aircrew training will be a priority with the introduction of the Mobile Threat Training Emitter System (MTTES). | The forecast variation is primarily attributable to foreign exchange updates. | EA-18G Growler Initial Operational Capability was declared in May 2019. Availability of the FA-18F Super Hornet aircraft was substantially increased during 2018-19 culminating in successful Air Force deployment on Raise Train Sustain exercises. The capability upgrade program for both the F/A-18F Super Hornet and EA-18G Growler fleets continued though 2018-19. Incremental upgrades to software, training systems, Growler mission systems and weapons clearances are progressing. Planning and co-ordination for incorporation of the Advanced Growler project is underway. The sustainment budget was achieved.
Airborne Early Warning and Control System - AEWC | CAF20 | 216.523 | 224.0031 | 203.2849 | -21 | The Airborne Early Warning and Control weapon system comprises six aircraft and associated Ground Support Segments. Boeing Defence Australia as the prime contracting partner together with Boeing Defence Systems, Northrop Grumman Systems Corporation and British Aerospace Engineering Systems Australia, provide a performance based support arrangement for maintenance, logistics, engineering, training, and program management in order to support the capability. The focus in 2018-19 will be on the continued reform and implementation of commercial arrangements to better align with contemporary contracting arrangements. These reforms will review various support arrangements in order to continue to provide an efficient and effective outcome to Air Force. | The forecast variation is primarily attributable to foreign exchange updates. | The Airborne Early Warning and Control weapon system met all its operational objectives including its highly successful contribution to Operation OKRA. A key sustainment reform was the successful implementation of the Wedgetail Head Agreement. The Head Agreement better aligns with contemporary contracting arrangements and provides consistent and better value for money commercial arrangements across all contracts within Wedgetail products and projects. The financial variation is primarily due to delays in contract deliverables.
Multi Role Helicopter - Troop Lift Helicopters MRH90 | CA48 | 215.4714 | 234.0063 | 238.5354 | 5 | During 2017-18, MRH90 production deliveries were completed with the delivery of the final aircraft, which has reached 47 aircraft. In-Service Support is provided under a prime contract with Airbus Group Australia Pacific (AAP). The MRH90 fleet is located at: 5th Aviation Regiment in Townsville, Queensland; Army Aviation Training Centre in Oakey, Queensland; 808 Squadron in Nowra, New South Wales; and Airbus Group Australia Pacific’s deep maintenance facility in Brisbane. Aircraft availability continues to be a key focus for 2018-19, with work to optimise MRH90 scheduled maintenance arrangements continuing along with optimisation of operational maintenance support arrangements. Finalisation of Taipan First Of Class Flight Trails is currently scheduled for 3rd quarter 2018. The highest priority will be the sustainment effort to support Plan Palisade, the introduction of MRH-90 Taipan into 6 Aviation Regiment to commence acceptance of the Special Operations role from Black Hawk. This will commence with the first two aircraft being inducted in February 2019. | Aircraft availability continues to be a key focus for 2018-19, with work to optimise MRH90 scheduled maintenance arrangements continuing along with optimisation of operational maintenance support arrangements. Further development of Taipan First Of Class Flight Trails is currently scheduled for 2nd Quarter 2019. The forecast variation is due to the Collective Bargaining Arrangements with Nahema being signed off for the realisation of technical and economic benefits for the international NH90 community and to address the forecast Rate of Effort and capability modifications under the Prime Contract. | The Taipan First of Class Flight Trials on Landing Helicopter Dock, HMAS Adelaide, completed in Quarter 2 of 2019. Aircraft continue to be delivered into the 6th Aviation Regiment as part of Plan Palisade. Collective contracting arrangements through NAHEMA continue to mature, but have experienced some delay due to the involvement of multiple nations. The achieved rate of effort for 2018-19 was less than forecast due to aircraft availability, which has been impacted by supply chain issues. Supply chain performance is being addressed at the highest levels between Defence and industry partners in Australia and Europe. The financial variation is primarily due to product delivery ahead of schedule than the forecast payment against the MRH90 sustainment contract.
F/A-18 Hornet Weapon System | CAF02 | 189.8454 | 195.0166 | 168.4929 | -27 | The F/A-18 A/B Classic Hornet weapon system comprises 71 aircraft and related support systems. The weapon system is supported by Boeing Defence Australia as the weapon system support integrator together with a broad range of other Defence industry providers including General Electric, BAE Systems Australia, Raytheon Australia, RUAG Australia, Northrup Grumman and Cubic Defense Applications. During 2018-19, focus will continue on supporting the fleet to the Planned Withdrawal Date (PWD) of December 2021, managing ageing aircraft effects, and assuring operational capability effectiveness ‘to the last day’. This includes continuing the Life of Type Assessment and Extension Program to ensure the platform can safely attain its PWD. Increased priority will also be given to planning the strategic disposal of the fleet and associated equipment, inclusive of a measured fleet drawdown during the approach to PWD. A progressive retirement of select aircraft will commence during the period. | The forecast variation is primarily attributable to foreign exchange updates. | The F/A-18A/B Classic Hornet under flew its assigned annual rate of effort. Notwithstanding, Air Force achieved sufficient rate of effort to meet their directed Force Generation obligations and aircrew progression requirements. Classic Hornet planned withdrawal date is December 2021. Progressive withdrawal and disposal has commenced with twelve aircraft retired from the fleet during 2018-19. The financial variation is primarily due to the combination of some common services transferring to other Sustainment Schedules in advance of Classic Hornet retirement, opportunities being realised to reduce sustainment costs through harvesting of components from retired aircraft, and reduced costs for contracted simulator support.
Armed Reconnaissance Helicopter Weapons System | CA12 | 152.8216 | 145.0452 | 145.0869 | 0 | All 22 Tiger armed reconnaissance helicopters are in-service in the final mature configuration. In-Service Support is provided under a prime contract with Airbus Australia Pacific (formerly Australian Aerospace). Final Operational Capability for Tiger was declared in 2016 with nine caveats. The two remaining open caveats are achievement of 5300 flying hours per year and treatment of Communication and Mission Management system weaknesses. During 2018-19, activity will focus on engineering developments to rectify Final Operational Capability caveats and the development of the Tiger’s amphibious capability for operations in the new Canberra Class Landing Helicopters docks. Key areas of sustainment activity have focussed on the refinement of the through life support arrangements to reduce overall cost of ownership for Defence, and improvement of aircraft availability and reliability. The Tiger Armed Reconnaissance Helicopter is a credible, capable aerial attack and reconnaissance system that is currently employed on operations by key European nations. | Final Operational Capability for Tiger was declared in 2016 with nine caveats. The final two caveats where closed by Chief of Army on the September 2018. During 2018-19, focus remains on the development of the Tiger’s amphibious capability for operations in the new Canberra Class Landing Helicopters docks and preparation for USA WAVERIDER 2019 to be conducted in 2019-20. The forecast variation is due to the latest forecast in Rate of Effort and scheduled completion of some minor Engineering Modifications. | The Tiger Armed Reconnaissance Helicopter capability achieved a record rate of effort through 2018-19 and was successfully embarked on Landing Helicopter Docks on multiple occasions. The relationship between Defence and Airbus Australia Pacific continues to mature, with recent initiatives further integrating staff in order to achieve 'Best for Defence' outcomes. The Tiger Through Life Support Contract Award Term Extension was endorsed by Minister of Defence in April 2019. This will provide certainty to the Tiger system through to 2025 while also delivering cost of ownership efficiencies. The Tiger Capability Assurance Program has secured funding to treat essential obsolescence and life limited parts, and is intended to continue in tranches through to the Tiger planned withdrawal date. The sustainment budget was fully achieved.
C-17 Heavy Air Lift Weapons System | CAF19 | 125.8974 | 133.2974 | 109.3551 | -24 | The C-17A Globemaster capability comprises eight aircraft and associated training devices (including a flight simulator). The majority of sustainment support for aircraft and training systems is provided via US Air Force Foreign Military Sales global support arrangements for the worldwide C-17A fleet. These global sustainment arrangements are supplemented by complementary Australian-based support, provided by Boeing Defence Australia. For 2018-19, the key focus continues to be maturing increased local Boeing Australia support (which commenced in October 2017) and support to operations. | The forecast variation is primarily attributable to contract efficiencies achieved by the United States Air Force on behalf of the global fleet of C-17A Globemaster III aircraft, resulting in reduced sustainment costs for engines, as well as foreign exchange updates. | The C-17 Globemaster III achieved its assigned rate of effort in national tasking and support to operations, including to the Middle East and to the Australian Antarctica Territory. The major sustainment activities this year included an upgrade to the Operational Flight Trainer system hardware, and fleet embodiment of a number of modification activities including Friend/Foe technology and realignment of the heavy maintenance cycle from five to six years. The financial variation is primarily due to contract efficiencies achieved by the United States Air Force on behalf of the global fleet of C-17A Globemaster III aircraft, resulting in reduced sustainment costs for engines.
MH-60R Seahawk Romeo Helicopter | CN35 | 124.0208 | 118.6592 | 142.6241 | 24 | Project AIR 9000 Phase 8 has delivered all 24 Seahawk Romeo aircraft, with the final delivery to Australia occurring in September 2016. Six minor Australian-led modifications are being progressively embodied in the aircraft by the Nowra-based Industry partner 'Maritime Helicopter Support Company'. The Seahawk Romeo capability is operated from HMAS Albatross in Nowra and is currently supporting six embarked flights on Navy ships. It will continue to grow to a mature state of eight embarked flights during 2018-19. | As of December 2018, the Seahawk Romeo capability is supporting eight embarked flights in Navy ships. Australian-led modifications to the aircraft have been progressively embodied with the program scheduled for completion in the second quarter of 2019. The forecast variation is due to reduced support requirements of Seahawk Romeo sustainment delivery activities. | The Seahawk Romeo capability has been supporting eight embarked flights on HMA Ships since December 2018 and on schedule. Final Operational Capability is forecast for 2023, when the third and final Hobart Class Destroyer is modified for embarked operations. The financial variation is primarily due to the support contract extension for Seahawk Romeo sustainment delivery activities.
Lead-In Fighter Hawk 127 Weapon System | CAF03 | 122.8626 | 134.9922 | 169.61 | 35 | The Lead-In Fighter fleet consists of 33 Hawk 127 aircraft and associated ground and related support systems. BAE Systems Australia Limited provides total logistics support for the Hawk 127 fleet under an In-Service Support contract, with operations at RAAF Base Pearce and RAAF Base Williamtown. During 2018-19, the focus will be on extending the In-Service Support contract with BAE Systems Australia to increase the company's platform stewardship responsibilities, and finalise transition aspects of AIR 5438 Phase 1A – Lead-In Fighter Capability Assurance Program. | The forecast variation is primarily attributable to the inclusion of contracted services to provide the required level of Aerial Opposing Forces and Target Support within the Product Schedule, and foreign exchange updates. | The Hawk 127 Lead-in Fighter marginally under flew its assigned rate of effort. This was primarily attributable to a three week no-fly period while investigating an uncontained engine failure. All introductory fighter training objectives were achieved. A mid-life update of the 33 Hawk 127 aircraft was completed in March 2019. The Hawk 127 in-service support contract with BAE Systems Australia was extended by two years and expanded to increase the company's platform steward responsibilities. During 2018-19, a contract for ADF Jet Air Support transferred from Air Force to Lead-In Fighter Hawk 127 Weapon System. The financial variation is primarily due to inclusion of additional scope transferred from Air Force, such as Jet Air Support, which provides aerial opposing forces and target towing services.
C130J-30 Hercules Weapon System | CAF06 | 101.2628 | 105.1516 | 97.9603 | -7 | The C-130J Hercules fleet consists of 12 aircraft and associated devices (including a flight simulator). The C-130J is supported by two prime performance based contracts: Airbus Group Australia Pacific provides deeper level maintenance, logistics and engineering support for the aircraft, and StandardAero provides support for the propulsions system. During 2018-19, the focus will be on continuing fleet embodiment of Large Aircraft Infrared Countermeasures, Link 16 (military tactical data exchange network), frequency converters (to enable enhanced air-land integration) and micro vanes (to deliver fuel savings); progression of the AE2100D3 propulsions system compressor replacement program; and implementing through life support contract reform. | The forecast variation is primarily attributable to foreign exchange updates. | The C-130J-30 Hercules Weapon System achieved its assigned rate of effort in national tasking and support to operations, including to the Middle East. The major sustainment activities for the year included fleet embodiment of a number of modifications such as Friend/Foe technology, operation of the new Fuselage Trainer device and implementing contract reform. The sustainment budget was primarily achieved.
KC-30A Weapon System Multi-role Tanker Transport | CAF22 | 88.7224 | 90.2095 | 124.5009 | 34 | The KC-30A Multi Role Tanker Transport (MRTT) capability comprises six aircraft and related training devices (including a flight simulator). All six aircraft are capable of air-to-air refuelling from pod and boom systems, and airlift logistics support. A seventh aircraft will be delivered in late 2019. The capability is supported by Northrup Grumman Australia, Airbus Defence and Space, and CAE. The focus will remain on maturing sustainment processes, while continuing to support military operations and the expansion of aircraft types certified as capable of air-to-air refuelling from the KC-30A. | The forecast variation is primarily due to the improved enterprise maturity and understanding of the numbers and types of spares and consumables required support the fleet rate of effort, including emergent issues and foreign exchange updates. | The KC-30 Multi Role Tanker Transport weapon system achieved its assigned rate of effort in national tasking and support to operations, including the Middle East Region and supporting the delivery of the first four F-35 Joint Strike Fighter aircraft to Australia. The major sustainment activities this year included fleet embodiment of a number of modifications such as improved software for the Aerial Refuelling Boom System and Identification Friend/Foe technology, as well as hardware upgrades to the pilot simulator visual systems. The financial result is primarily due to the improved maturity and understanding of the numbers and types of spares and consumables required to support the fleet rate of effort. There is a distinct likelihood of needing additional funding above current baseline guidance across future years. This will be addressed during the current Defence Management and Financial Plan review process.
P-8A Poseidon Maritime Surveillance Aircraft | CAF35 | 87.0791 | 109.253 | 112.0638 | 3 | AIR 7000 Phase 2B will acquire 12 manned Maritime Patrol & Response Aircraft (P-8A Poseidon), mission support & training systems and facilities as partial replacement of the AP-3C Orion aircraft. Six of the 12 Poseidon aircraft have been delivered, with the last aircraft due for delivery in February 2020. Initial Operating Capability was achieved on 20 March 2018. During 2018-2019, the focus will be on developing a mature through-life sustainment construct, whilst maintaining agreed Air Force availability performance requirements. Two of three Mobile Mission Support Systems have been delivered, with the third due in late 2019. The Training Support Facility is due to commence training for the first group of Australian Aircrew in July 2018. | The forecast variation is due to the realignment of sustainment delivery activities from AP-3C Orion Weapon System, as well as foreign exchange updates. | The P-8A Poseidon Weapon System exceeded its assigned rate of effort in national tasking and support to operations with the P-8A fleet achieving modest overfly in 2018-19. The major sustainment activities this year focussed on working with the United States Navy to address some limitations around sparing and responsiveness of engineering support, as well as optimising the P-8A support system to satisfy forecast future needs. The sustainment budget was primarily achieved.
C-27J Spartan Battlefield Airlifters | CAF34 | 66.4263 | 67.9325 | 57.111 | -11 | The C-27J Spartan fleet consists of 10 aircraft, with the training system yet to be delivered. The C-27J is supported by two prime performance based contracts. Northrop Grumman Australia provides logistics and engineering support for the aircraft, and StandardAero provides support for the propulsions system. During 2018-19, the focus will be on maturing the overall C-27J sustainment system and the support contracts, with a focus on maturing sustainment processes. | The forecast variation is primarily attributable to foreign exchange updates. | The C-27J Spartan fleet consists of 10 aircraft, with the training system yet to be delivered. During 2018-19, the fleet of 10 C-27J Spartan aircraft relocated from RAAF Richmond to RAAF Amberley. The sustainment system is still maturing to reliably support C-27J tasking and training activities from RAAF Amberley. The financial variation is primarily due to the realignment of activities and maturing performance.
AP-3C Orion Weapon System | CAF04 | 61 | 51.6718 | 47.6491 | -4 | The AP-3C Orion maritime intelligence, surveillance, response and electronic warfare weapon system comprises of up to eight aircraft, simulators and ground based systems. The weapons system is supported primarily by industry partners: Airbus Group Australia Pacific (AGAP), Raytheon Australia, BAE Systems Australia (BAES), General Dynamics Canada (GDC) and Lockheed Martin (LM) for engineering, maintenance and supply support. During 2018-2019, the focus will be to transition sustainment arrangements to reduce rates of production in conjunction with aircraft retirement; supporting operations while supporting demilitarisation, gifting and sales of retiring aircraft; and conducting sales or disposal of excess inventory and support equipment. | The forecast variation is primarily attributable to the net of the realignment of sustainment delivery activities to P-8A Poseidon Maritime Surveillance Aircraft and the amalgamation of the Electronic Warfare Mission Support System into the AP-3C Product Schedule. | The AP-3C Orion Capability achieved its assigned rate of effort in national tasking and support to operations in 2018-19. The major sustainment activities this year focussed on aircraft disposals/sales, inventory and support equipment reduction and the rebaselining of on-going commercial support arrangements to appropriate levels to support the small AP-3C fleet to Planned Withdrawal Date. The financial variation is primarily due to reduced disposal costs achieved by leveraging contracted workforce efficiencies, avionics contract re-negotiations and a greater than expected reduction in repairable item repairs and breakdown down spares usage due to fleet retirement.
Joint
Air Force Munitions and Air Force Guided Weapons | CAF32 & CAF33 | 91 | 95 | 78 | -17 | Air Force munitions and guided weapons comprise guided missiles, bomb bodies, fuses and guided bomb components; and inert and training bombs employed by Air Force Platforms. The inventory also includes countermeasures, impulse cartridges, cannon ammunition, safety pyrotechnics and emergency egress power and cartridge actuated devices. The variation is due to an underspend due to the transfer of explosive ordnance manufacturing activities aspects to the newly established Explosive Ordnance Manufacturing Facilities product. This was partially offset by procurement of additional guided weapons. | The forecast variation is primarily attributable to foreign exchange updates. | The financial variation is primarily due to the transfer of explosive ordnance manufacturing aspects to another facility. This was partially offset by procurement of additional guided weapons.
Army Munitions and Army Guided Weapons | CA59 & CA60 | 207 | 160 | 151 | -9 | Army munitions and guided weapons inventory includes both guided and non-guided explosive ordnance, primarily supporting Army. Ammunition types include small arms ammunition, cannon, artillery, mortar, tank, rockets, missiles and guided weapons. During 2018-19 steady improvement to overall fleet management of land explosive ordnance continued, with improved demand and supply planning. The variation is due to an underspend due to supply issues relating to the procurement of Combat Support Munitions. | The forecast variation is primarily attributable to the transfer of explosive ordnance manufacturing aspects to Explosive Ordnance Manufacturing Facilities, and foreign exchange updates. | The financial variation is primarily due to supply issues relating to the procurement of Combat Support Munitions.
Air Traffic Control Capability | CAF12 | 64 | 68 | 52 | -16 | This product continued to support the Defence Air Traffic Management system, consisting of fixed and deployable sensors, data processing, displays, navigation aides, command control and communications systems and inter-faces. The variation is due to an underspend due to delays in later than expected delivery of Air Traffic Control activities including Transportable Air Operations Tower (TAOT) and Fixed Tactical Air Navigation (FTACAN) works. | The forecast variation is attributable to genuine savings through contract consolidation and Smart Buyer best practices and realisation of risks attributed to project delays. Rescheduling procurement and installation of Fixed Tactical Air Navigation Systems, Instrument Landing Systems, AIR5431 PH1 Deployable ATM systems, AIR5431PH2 Hendsoldt Radar Systems, AIR5431PH3 Civil Military Air Traffic Management System and disposal of legacy ATM systems negatively impacted budget increasing the variance. | The financial variation is due to delays in delivery of Air Traffic Control activities including Transportable Air Operations Tower and Fixed Tactical Air Navigation works.
Navy Munitions and Navy Guided Weapons | CN38 & CN37 | 108 | 97 | 201 | 104 | This product supports both Navy Munitions and Navy Guided Weapons. Navy munitions consists of Navigational Outfits, Medium and Large Calibre Gunnery, Pyrotechnics and Cartridge Actuated Devices, Countermeasures, Force Protection and demolition products utilised by Navy. Navy's Guided Weapons are categorised into four main areas: Missiles, Mine Warfare, Heavy Weight Torpedoes and Lightweight Torpedoes. Navy's Guided Weapons Explosive Ordnance activities also includes sustainment of Guided Weapons used by Army and Air Force where Navy is the lead service. The variation is due to the earlier than expected payments to the US for Missiles. | The forecast variation is primarily attributable to the transfer of explosive ordnance manufacturing aspects to Explosive Ordnance Manufacturing Facilities, and foreign exchange updates. | The ADF's inventory consists of both Navy Munitions and Navy Guided Weapons. Navy munitions consists of Navigational Outfits, Medium and Large Calibre Gunnery, Pyrotechnics and Cartridge Actuated Devices, Countermeasures, Force Protection and demolition products utilised by Navy. Navy's Guided Weapons are categorised into four main areas: Missiles, Mine Warfare, Heavy Weight Torpedoes and Lightweight Torpedoes. Navy's Guided Weapons Explosive Ordnance activities also includes sustainment of Guided Weapons used by Army and Air Force where Navy is the lead service. The financial variation is primarily due to a revised payment schedule for a number of supplies.
Wide Area Surveillance | CAF13 | 89 | 89 | 90 | 1 | This product continued to support the Jindalee Operational Radar Network (JORN) and space surveillance systems. The variation is due to an earlier than expected contract payments associated with JORN. | The expenditure against the planned budget is on track. | The financial variation is primarily due to product delivery ahead of the expected contract payment schedule for Jindalee Operational Radar Network. This was partially offset with the delay in finalisation and payment of contract change proposals required to the Core Contract.
Land
ADF Clothing | CA39 | 113.4258 | 111.383 | 109.7385 | -2 | ADF Clothing comprises approximately 21,000 line items of uniform, footwear and other items supplied by the textile, clothing and footwear industry. During 2018-19, the key activities will include: • provision of combat clothing to operations; • the continued manufacture and delivery of the Australian Multicam Uniforms and preparation for the roll out of the new Maritime Multicam Pattern Uniform to Navy; • ongoing development of uniform enhancements across both combat and the non-combat uniform suite for Navy, Army and Air Force; and • procurement to meet the ADF’s clothing and footwear requirements for the ADF's raise, train and sustain activities. | The product continues to meet the ADF’s clothing and footwear requirements. The forecast variation reflects revised demand planning and inventory targets that have resulted in cost savings that have been reallocated to existing sustainment funding pressures. | During 2018-19, the provision of combat clothing to operations; continued manufacture and delivery of the Australian Multicam Uniforms; ongoing development of uniform enhancements across both combat and the non-combat uniform suite for Navy, Army and Air Force and procurement to meet the ADF’s clothing and footwear requirements for the ADF's raise, train and sustain activities. The financial variance was primarily due to later than planned delivery of uniform items, and less than expected usage of ceremonial items.
ADO Commercial Vehicles Fleet | CA19 | 79.744 | 77.922 | 71.5186 | -6 | The Australian Defence Organisation’s Commercial Vehicle Fleet comprises approximately 5,900 Defence owned Commercial vehicles and trailers. The fleet ranges from passenger sedans through to heavy rigid trucks, touring coaches and aviation refuelling vehicles. An additional 30 road-train systems are leased under the program. During 2018-19, approximately 1,060 passenger and light-medium commercial vehicles are scheduled to be replaced with a like to like vehicles as part of a rolling replacement program. In 2018–19, the fleet will continue to focus on improving overall vehicle utilisation and rationalisation and reducing costs. | The product continues to focus on improving overall vehicle utilisation and rationalisation and reducing costs. The forecast variation is the result of enhancements to fleet management and vehicle replacement planning that has been driven by improvements in the data being provided by the whole of government Fleet Services Contractor. | During 2018-19, approximately 977 passenger and light-medium commercial vehicles were replaced as part of a rolling replacement program, as planned. The financial variation was primarily due to cost efficiencies through access to a wider vehicle market, and improved data for managing fleet replacements.
Health Systems | JHC01 | 52.969 | 60.9876 | 60.4733 | -1 | The Health Sustainment Fleet provides pharmaceutical, medical and dental consumables and equipment to support ADF Health Capability requirements. During 2018-19, the key activities will include provision of health materiel to operations; and transition of medical and dental consumables into the Pharmaceuticals Prime Vendor arrangement. | The additional budget supplementation is due to bringing forward critical hardware procurements into 2018-19 for continued modernisation across operational and garrison health services. | The Health Sustainment Fleet has provided health materiel to operations; and transitioned medical and dental consumables into the Pharmaceuticals Prime Vendor arrangement. Customer demand has been met and the savings achieved against Pharmaceuticals and Medical & Dental Consumables have been reinvested where possible to Medical and Dental Equipment procurements. The financial variation is primarily due to the net value of savings that have been achieved.
Maritime
Adelaide Class Frigate | CN01 | 70.2419 | 74.0538 | 71.4547 | -3 | The support objective is to maintain the materiel capability of the Adelaide Class Frigates through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities. During 2018-19, the focus will be on completing the scheduled ship maintenance activities for HMA Ships Newcastle and Melbourne, and to undertake the disposal of ex HMAS Darwin. | The forecast variation is due to the SM2 project transitioning to sustainment and foreign exchange fluctuations. | The support objective is to maintain the materiel capability of the remaining Adelaide Class Frigates through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities. The financial variation is primarily due to a number of previously planned payments moving to early July 2019 and will now be paid in 2019-20. Disposal options are being developed, with ex-HMAS Newcastle decommissioned in June 2019 and HMAS Melbourneto be decommissioned in September 2019.
Anzac Class Frigate | CN02 | 374.3662 | 366.5218 | 364.2004 | -2 | The support objective is to maintain the materiel capability of the eight Anzac Class Helicopter Frigates through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities. During 2018-19, the focus will be on completing the scheduled Anzac Class maintenance activities, and the successful installation and integration of Anzac Midlife Capability Assurance Programme (AMCAP) inclusive of Platform Systems Remediation, SEA 1442 Phase 4 Maritime Communications Modernisation Project, and SEA 1448 Phase 4B Anzac Air Search Radar Replacement on HMAS Arunta as first-of-class. | There will be no significant variation to financial estimate for delivery of Anzac Class Frigate. | The support objective is to maintain the materiel capability of the Anzac Class Frigates through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities. There was no significant variation to financial estimates for the sustainment of the Anzac Class Frigates in 2018-19.
Armidale Class Patrol Boat | CN09 | 69.7273 | 98 | 98.4693 | 0 | The Patrol Boat Enterprise Program objective is to sustain the Armidale and Cape Class Patrol Boats materiel capability, minimise the cost of ownership and provide sustainable cost effective maintenance, design, engineering and logistical support for the platform and systems through agreements with industry partners. During 2018-19 the aim is to improve performance achievement of required capability in line with operational requirements. | The forecast variation is due to additional planned and corrective maintenance requirements identified by the In Service Support Contractor. | The sustainment budget was achieved through full delivery of the annual work program of Planned and Corrective maintenance, management of inventory purchases and engineering changes. Costs were partly offset by recognition of Operation Resolute funding.
Hobart Class Destroyer | CN40 | 163.1001 | 160.8831 | 159.8523 | -1 | The products required to establish sustainment capability prior to the delivery of three Destroyer Designated Guided (DDGs) to the Navy. The execution of the CN40 contracts are as a result of defining the sustainment contracts within the SEA4000 Acquisition Program. The majority of the contracted costs spent in 2018-19 will be on the Foreign Military Sales Case, purchase of spares and support services, along with Managing Contractor costs. The Managing Contractor (BAE Systems) were appointed in December 2016 and are working with the DDG SPO to establish the support capability for the DDGs. | There will be no significant variation to financial estimates for delivery of Destroyer Designated Guided (Air Warfare). | The support objective is to maintain the materiel capability of the Hobart Class Destroyers through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities as this capability is introduced into service. There was no significant variation to financial estimates for the sustainment of the Hobart Class Destroyers in 2018-19.
Collins Class Submarine | CN10 | 591.6718 | 595.1886 | 654 | 59 | The Collins Program objective is to sustain the Collins class submarine materiel capability (including the associated escape and rescue capability), minimise the logistic costs of ownership, and provide sustainable and cost effective design, engineering and logistics support for platform systems and combat systems, through agreements with industry partners including ASC Pty Ltd, Raytheon Australia, Thales Australia, BAE Systems, PMB Defence and other providers. The Coles Report into the business of sustaining Australia’s strategic Collins class submarine capability of November 2012 has been seminal in catalysing improved submarine availability since 2012, with the attainment of Coles' benchmark availability levels achieved in 2016-17. In collaboration with Navy and industry (and as recommended by Coles), Defence has established an enterprise approach to the Collins Program. The follow-up Coles Review 'Beyond Benchmark' released in October 2016, reported a remarkable improvement in the sustainment of the class. During 2018-19, the focus will be to preserve the Program performance through sustained delivery of required capability at benchmark availability; maintain regional superiority through timely delivery of Collins capability upgrades; attain benchmark support system efficiency materiel cost of ownership by 2022-23; and manage Collins submarines through to withdrawal cognisant of capability continuity and transition to a Future Submarine force. | Expenditure is as per work program and full achievement is expected. | The Collins Class Submarine Program objectives are to sustain and enhance the Collins submarine capability, deliver the required availability, and reduce logistic cost of ownership. These objectives are being met through long-term in-service support contracts with industry partners ASC, Raytheon, Thales, BAE, PMB Defence and James Fisher Defence. Submarine availability above the international benchmark was achieved for a third consecutive financial year in 2018-19, submarines conducted several overseas deployments and capability upgrades on the Collins control system, external communications and sonar system are progressing well. The financial variation is primarily due to an acceleration in contract milestones and critical stock procurement and Combat System Joint Project Office payments.
Hydrographic Support | CN46 | 68.1801 | 74.0869 | 69.6628 | -4 | The Hydrographic Survey system comprises two Leeuwin Class Hydrographic Ships (HS), four Paluma Class Survey Motor Launches (SML) and six Survey Motor Boats (SMB) embarked in the HS. Sustainment of the Hydrographic Survey System is through a prime contracting partner that provides a performance based support arrangement for maintenance, logistics, engineering, training, and program management in order to support the capability. In addition it includes the Laser Airborne Depth Sounder II (LADS) system and its host, the Dash 8-200 aircraft and Antarctic Survey Vessel (ASV) and other Hydrographic Survey Platforms. During 2018-19, the focus will be the implementation of commercial initiatives to better align with contemporary contracting arrangements. These reforms will review various support arrangements to ensure they provide the most efficient and effective outcomes in support of capability platforms. | The forecast variation is due to the introduction into service of the Rapid Environmental Assessment capability and safety and seaworthiness requirements for the Hydrographic fleet. | The financial variation is primarily due to rephrasing of payments and a delay in to the Rapid Environmental Assessment Capability project transferring to the Hydrographic Support Program from acquisition. In addition, engineering annual program of work (safety and seaworthiness requirements) has experienced delays.
Canberra Class Landing Helicopter Dock | CN34 | 117.9108 | 127.7807 | 133.6888 | 6 | The support objective is to maintain the materiel capability of the two Canberra Class Landing Helicopter Dock (LHD) vessels and 12 LHD Landing Craft (LLC), through the provision of materiel support and ongoing maintenance of the ships and associated equipment, systems and operator training facilities. During 2018-19, the focus will be on completing the scheduled LHD/LLC maintenance activities; bedding in a new supplier model that aligns more closely with the intent of the First Principles Review; improving the baseline support system products and systems; and supporting the remediation activities of JP2048 Ph3 and Ph4A/B. | The forecast variation is due to funding adjustments for additional identified engineering activities and support requirements. | The scope of this product addresses the sustainment of two Canberra Class Landing Helicopter Dock (LHD) vessels, 12 LHD Landing Craft (LLC), and associated shore-based systems and facilities by meeting seaworthiness, materiel confidence, and cost efficiency demands. This will enable the LHD to deliver integrated combat capabilities in amphibious warfare, humanitarian assistance, disaster relief and sealift. The financial variation is attributed to the conduct of additional engineering design work, inventory, planned and corrective maintenance requirements.
Maritime Cross Platform | CN49 | 64.4277 | 78.7832 | 62.6494 | -16 | This product schedule is responsible for the sustainment of seaworthy materiel that is common across multiple platforms and for which Maritime Cross Platform Systems Program (MCPSPO) is the identified Designated Logistics Manager. The materiel includes items related to combat systems, platform and propulsion systems, and survivability systems e.g. safety and internal platform communications. During 2018-19, the product schedule will be significantly reviewed to reflect a revised configured baseline being developed as part of MCPSPO reform activity. The revised schedule will be expanded to better articulate required sustainment levels, technical responsibilities and certification requirements. | The forecast variation is due to funding provided to Maritime Cross Platform for additional procurement of common material across multiple Navy platforms. | The variation is attributed to planned payments occurring in early July 2019 and the late receipt of combat related support and test equipment and will now be paid in the 2019-20.
Mine Hunter Coastal | CN14 | 66.0901 | 69.8861 | 58.5461 | -11 | The support objective is to maintain the capability of the four Huon Class Mine Hunter Coastal vessels and associated shore-based systems and facilities through the provision of materiel support and ongoing maintenance of the in-service ships. In 2018-19 the focus will be on the sustainment of obsolescence aspects leading up to the Service Life Extension project (SEA 1179). | The forecast variation increase is due to additional activities undertaken and subsequent adjustment to planned and corrective maintenance work. | The variation is primarily due to delays in planned maintenance arising from changes in the ship deployment schedules and a defect in HMAS Yarra main engine, delays in implementing obsolescence rectification activities, delays in invoicing for inventory items through the Military Integrated Logistic Information System and invoices that were delayed for payment from June to July.
Total -Top 30 Products |  | 4358 | 4450.0032 | 4541.6322 | 92
Other approved Sustainment Product |  | 1660 | 1934.9368 | 2045.9832 | 111
Total Sustainment Product Funds Available |  | 6017.9965 | 6384.94 | 6587.6153 | 203
Support to Operations |  | 323.291 | 323.291 | 182.5327 | -141
Total Sustainment and Operations Funding |  | 6341.2875 | 6708.231 | 6770.148 | 62

## Table D.2
Web Table D.2: Top 30 - Acquisition Projects by expenditure, 2018-19
Project Name | Project number and phase | Approved project expenditure $m | Cumulative expenditure to 30 June 2018 $m | Budget estimate 2018-19 $m | Revised estimate (1) 2018-19 $m | Final plan (2) 2018-19 $m | Actual expenditure (3) 2018-19 $m | Variation $m | Project update and explanation of variation 2018-19
[6 empty] | (a) | (b) | (b-a)
Air
New Air Combat Capability Initial Aircraft and Additional Aircraft to form 3 Squadrons | AIR 6000 Phase 2A/B | 16522.644 | 2669.4631 | 1821 | 1933 | 1977.6488 | 1942.0441 | -36 | During 2018-19, the project delivered the last four Lot 10 aircraft and the first four Lot 11 aircraft. Contracts for the next 15 Lot 12 aircraft are scheduled to be signed in August 2019. The first two Australian F-35A aircraft arrived in December 2018 and are now based at RAAF Williamtown. The Australian Validation and Verification program commenced in early 2019. Training continues in the USA but elements of both pilot and maintainer training commenced at RAAF Williamtown in 2018-19. The Australian Reprogramming Laboratory commenced operation in the United States, providing its first mission data file for our aircraft in February 2019. The project primarily achieved its budget.
Maritime Patrol and Response Aircraft System | AIR 7000 Phase 2 | 5375.7725 | 3428.0076 | 592 | 409 | 472.5941 | 472.4384 | 0 | The project took delivery of the eighth aircraft, fitted with a structural loads monitoring system. Planning continued for delivery of the third and final Mobile Tactical Operations Centre (due for final acceptance in late 2019), as well as the first upgrade to the P-8A aircrew and maintenance training systems. Delivery of the final four aircraft will commence from July 2019. The project achieved its budget.
Pilot Training System | AIR 5428 Phase 1 | 1250.6758 | 324.3492 | 403 | 379 | 343.2679 | 356.7276 | 13 | During 2018-19, the project delivered 23 training aircraft (for a progressive total of 36), six flight simulators, training courseware and associated learning environment elements to support the pilot and flying instructor training at RAAF East Sale, Victoria which commenced in January 2019. Work to validate the new Pilot Training System has progressed well. Flight Training Devices, Simulators and Course have been progressively developed through cooperation between the Industry and the Commonwealth. The financial variation is primarily due to the early delivery of aircraft and flight simulator and associated payments, courseware and other relevant activities.
Multi-Role Helicopter (MRH) | AIR 9000 Phase 2 | 3770.9906 | 3111.2539 | 186 | 148 | 133.7071 | 104.8229 | -29 | This project is acquiring 47 MRH-90 multi-role helicopters for the Army and the Navy. Phase 2 acquired 12 MRH-90s for an additional Army air-mobile squadron. Phase 4 replaces the Black Hawk fleet. Phase 6 replaced the Navy’s Sea Kings. The introduction of the MRH90 into 6 Aviation Regiment in support of Special Operations as well as key capabilities for Army and Navy operations was the key focus in 2018-19, including a replacement Cargo Hook, Fast Roping Rappelling and Extraction System and Gun Mount. The financial variation is primarily due to the re-prioritisation of delivery of key capabilities to support integration of MRH-90 into 6 Aviation, with non-essential elements being delayed.
Airborne Early Warning & Control Interoperability Compliance Upgrade | AIR 5077 Phase 5A | 1192.693 | 440.3666 | 215 | 177 | 159.845 | 165.6515 | 6 | Delivery of the two interim aircraft and associated support systems has been delayed by approximately 3 months as a result of additional software fault rectification effort necessary to declare the capability operational. The detailed design review for the Release 2 additional interoperability upgrades was achieved in May 2019. The project primarily achieved its budget.
EA-18G Growler Airborne Electronic Enabling Capabilities | AIR 5349 Phase 3 | 3510.3418 | 2300.6894 | 197 | 193 | 175.3065 | 127.1666 | -48 | The project achieved Initial Operating Capability in May 2019, representing a significant milestone in the delivery of an Electronic Attack capability to Air Force. The project has also achieved an initial service release of the Mobile Threat Training Emitter System (MTTES) to 82WG to support aircrew training in the ranges west of Amberley. The MTTES capability was demonstrated at Delamere Weapons Range in the Northern Territory during Exercises. Australian aircrew training in the United States continues and the project has delivered the last of the Maintenance training requirements to Air Force. The financial variation is primarily due to the Foreign Military Sales payment occurring in July 2019.
Future Naval Aviation Combat System | AIR 9000 Phase 8 | 3212.5965 | 2220.4708 | 139 | 167 | 142.0458 | 117.6592 | -24 | The Seahawk Romeo capability has been supporting eight embarked flights on HMA Ships since December 2018 which is in accordance with the planned schedule. Final Operational Capability is forecast for 2023, when the third and final Hobart Class Destroyer is modified for embarked operations. The financial variation is primarily due to delayed weapons deliveries and Foreign Military Sales payment occurring in July 2019.
Helicopter Aircrew Training System | AIR 9000 Phase 7 | 481.5794 | 293.2457 | 90 | 89 | 88.4628 | 91.9837 | 4 | The project initial helicopter training courses were successfully completed, with courses continuing to be graduated throughout 2019 under sustainment activities. The Squirrel and Kiowa Helicopters have now been retired. Final Acceptance was signed in March 2019 and the operations transitioned from acquisition to sustainment. Final Operational Capability is planned to be achieved by mid 2020. The financial variation is primarily due to a price variation on Final Acceptance.
Conversion of additional KC-30A to multi-role Tanker Transport | AIR 7403 Phase 3 | 894.273 | 590.2938 | 78 | 60 | 53.0614 | 42.1 | -11 | During 2018-19, the project delivered the second additional Multi Role Tanker Transport aircraft with the Government Transport and Communications capability. The financial variation is primarily due to the retirement of risk within the prime contract and a revised schedule for the delivery of spares and support equipment.
Battlefield Airlift - Caribou Replacement | AIR 8000 Phase 2 | 1442.0615 | 785.4648 | 68 | 69 | 55.6664 | 47.9069 | -8 | During 2018-19, the project placed the wing fatigue testing Flight Loads Test Program on contract under the Structural Substantiation Program (SSP). The requirements for the remaining SSP scope coupled with the avionics upgrade are being matured, therefore are not yet on contract. Work to establish training devices, including a flight simulator, continues with a contract expected to be signed in 2019-20. Acquisition spares, repairable items and test equipment procured by the project have been correctly receipted, codified and catalogued and entered the supply pipeline. Minor non-critical support items due to be delivered in 2019-20. One aircraft has been modified with the latest Identification Friend or Foe equipment by the original manufacturer in Italy. The remainder fleet is being prepared for modification in Australia. The financial variation is primarily due to the reprogramming of aircraft modification contract schedules to better reflect latest requirements and a revision to spares procurement requirements.
Airborne Early Warning and Control Acquisition | AIR 5077 Phase 3 | 3890.3363 | 3630.4653 | 55 | 43 | 31.5283 | 26.1957 | -5 | A range of radar and mission system remediation activities have been progressed. Development of a radar multi channel recorder was significantly delayed by technical challenges but is now progressing. Development of radar host processor software was delayed a few months due to resource contention. The financial variation is primarily due to delays in the Radar Multi Channel Recorder and Host Processor Software developments.
Joint
Battlefield Command Systems (Tranche 2) | LAND 200 Phase 2-A | 961 | 99 | 206 | 227 | 226 | 223 | -3 | The Battlefield Command System (Tranche 2) provides Army with a Tactical Communications Network (that includes digital radios and software applications to plan and manage the network) and an integrated Battle Management System designed to transform command and control of Land forces from a paper-based system to a modern digital system. The Battlefield Command System (Tranche 2) will integrate the Battlefield Command System into 540 new platforms (M1A1 Tank, M88 Armoured Recovery Vehicle, Medium Heavy Cargo Trucks, Protected Mobility Vehicle – Light, and Protected Mobility Vehicle – Medium (Gateway)); enhance software delivered by Tranche 1; deliver a new Enterprise Battle Management System (BMS-C2) software license; deliver a new Tactical Communications Network; deliver a new Weapon Integrated Battle Management System; and embed training into the Army’s individual and collective training institutions. The project completed several Design Reviews for both Tactical Communications Network and Battle Management System. The project has commenced hardware delivery to support Battle Management System training across Army’s training establishments and has completed the installation of communication components into 150 Medium Heavy Cargo trucks. The financial variation is due to delays in the execution of the Vehicle Integration Contract Change Proposals.
Battlespace Communications System (Land) | JP 2072 Phase 2B | 943 | 332 | 136 | 165 | 151 | 158 | 7 | The Release 1 of capability was fully delivered to Army and Air Force Units by December 2018, with the completion of the Introduction Into Service Training occurring in April 2019. The Release 2 of capability Detailed Design Review was successfully conducted in December 2018, followed by the successful Support System Detailed Design Review in February 2019. The financial variation is primarily due to achieving two milestones ahead of the contract schedule.
Fixed Base Defence Air Traffic Management & Control System (Ph 3-Combined RFT) | AIR 5431 Phase 3 | 976 | 155 | 116 | 125 | 115 | 109 | -6 | During 2018-19, the project achieved a number of mandatory technical and schedule reviews, and progressed a number of changes to both Airservices' contract with Thales, and Defence's contract with Airservices, in order to integrate the collaboration options agreed between Airservices and Defence to address affordability issues prior to contract execution. The financial variation is primarily due to later than expected initiation of the Autotrac II Air Traffic Control System contract and lower than anticipated contracted workforce costs.
ADF Identification Friend or Foe and Automatic Dependent Surveillance - Broadcast | AIR 90 Phase 1 | 436 | 113 | 96 | 90 | 72 | 58 | -14 | Key deliverables in 2018-19 included the first-of-type installation on the Multi Role Tanker Transport aircraft (KC-30A), HMA Ships Sirius and Choules, the Huon Class Minehunters, and achievement of the Initial Operational Capability for the Robotsystem 70 (RBS 70) Ground Based Air Defence System. The financial variation is primarily due to later than expected delivery of some contract milestones associated with the Multi Role Helicopters upgrade, Tactical Air Defence Radars and the RBS 70 upgrades.
Satellite Ground Station (SGS) - East and Wideband SATCOM Network Management System | JP 2008 Phase 5B2 | 234 | 57 | 76 | 60 | 62 | 57 | -5 | The project achieved Detailed Design Review milestone in late 2018, and the Prime Contractor has achieved a number of facilities construction milestones slightly ahead of schedule. The project achieved its Detailed Design Review milestone in December 2018. The variation is primarily due to a re-scheduling of the factory acceptance testing of software and communications equipment. This re-scheduling will not impact on the planned initial material release date.
Jindalee Operational Radar Network (JORN) Phase 6 | AIR 2025 Phase 6 | 1118 | 42 | 71 | 66 | 56 | 49 | -7 | The project continued to deliver a major redesign and upgrade to Australia’s Jindalee Operational Radar Network (JORN), with the majority of electronics and software within the system to be updated to ensure that Australia remains at the leading edge of Over-The-Horizon-Radar technology beyond 2040. During 2018-19, the systems engineering program commenced and progress has been made towards completion of Systems Requirements Review. The software development program and hardware prototype development are also progressing in parallel. The financial variation is primarily due to delays within the systems engineering program.
Fixed Base Defence Air Traffic Management & Control System (Ph 2-Radar) | AIR 5431 Phase 2 | 202 | 76 | 60 | 73 | 30 | 22 | -8 | This project continues to work towards delivery of nine new Air Traffic Control Radars, replacing the existing Australian Defence Air Traffic System radars at RAAF Bases Darwin, Townsville, Amberley, Williamtown, Pearce, Naval Station Nowra and the existing ALENIA Sensors located at East Sale, Tindal and Army Aviation Centre Oakey. The financial variation is primarily due to the need to repair storm damaged equipment, address some production quality issues and to more generally improve the design of radar antenna.
Land
Overlander - Medium Heavy Capability (MHC) - Truck and trailer components | LAND 121 Phase 3B | 3399.8684 | 1662.8093 | 628 | 639 | 628.9294 | 586.7084 | -42 | This project will deliver 2707 vehicles in both protected and unprotected configurations, in an array of variants. The project will also acquire 1,753 trailers to enhance payload capacity and 3858 associated modules. Deliverables are progressing to schedule and the project is continuing to collaborate with AHQ in support of Army's Operational Test and Evaluation activity currently underway. These activities will contribute to the achievement of IOC due in December 2019. The financial variation is primarily due to minor delays in the delivery of medium recovery vehicles, liquid modules and engineering system reviews.
Overlander - Protected Mobility Vehicle - Light (Hawkei) | LAND 121 Phase 4 | 1979.5218 | 463.0749 | 396 | 203 | 117.4786 | 89.2707 | -28 | This project will acquire and deliver into service 1100 Hawkei Protected Mobility Vehicles - Light (PMV-L) and 1058 associated trailers. The PMV-L will perform command, reconnaissance, liaison and utility roles. The Production Reliability Acceptance Test (PRAT) is a key enabler for entry into Full-Rate Production and commenced in May 2019. Six vehicles will undertake mobility testing of approximately 32,000 km each and two further vehicles will undertake 'Static Silent Watch' testing, with a reduced mobility aspect of approximately 7,500 kilometres each. As at July 2019, the PRAT vehicles have completed a total of over 29,000km. The financial variation is primarily due to delays in the delivery of engine components.
Night Fighting Equipment Replacement | LAND 53 Phase 1BR | 442.572 | 110.5297 | 90 | 96 | 96.982 | 95.2805 | -2 | This project is replacing land-based night vision equipment and laser aiming devices that attach to specified weapons of the ADF. The financial variance is primarily due to savings in costs associated with weapons integration, lower than expected Tranche 1 consumables and support costs and delays in Tranche 2 trials.
Chemical, Biological, Radiological, Nuclear Defence (CBRND) | JP2110 Phase 1B | 253.4042 | 7.5336 | 54 | 24 | 17.3869 | 17.1772 | 0 | The project will deliver an improved Chemical, Biological, Radiological and Nuclear Defence (CBRND) capability, to enhance the protection of Australian Defence Force personnel against exposure to toxic industrial chemicals and weaponised CBRN agents in land and maritime environments. The project successfully negotiated acquisition and support contracts with the preferred tenderer in July 2018, and obtained contract signature for the Collective Training Simulation System and the Aircrew Individual Protective Ensemble system in February 2019 and March 2019 respectively. The project achieved its budget.
Soldier Enhancement Version 2 - Lethality | Land 125 Phase 3C | 463.382 | 278.7488 | 53 | 50 | 49.8329 | 33.8147 | -16 | This project will deliver the Enhanced F88 rifle, a Grenade Launcher Attachment, and a suite of Surveillance and Target Acquisition ancillaries, including an enhanced day sight and thermal and image intensifier sights. The financial variation is primarily due to a delay in entering contracts for the Capability Growth Program Enhancement program.
Maritime
Future Submarine Design and Construction | SEA 1000 Phase 1B | 5962.66 | 364.0896 | 418 | 456 | 414.7375 | 358.3214 | -56 | In February 2019, the Future Submarine Program Office and Naval Group signed the Strategic Partnering Agreement, under which the design and build of the Attack class submarine fleet will be conducted. In March 2019, the Program Office entered the Submarine Design Contract with Naval Group for the design phase of the project. The financial variation is primarily due to invoices delayed from June to July, and a reduction in project-related activities reflecting lower than anticipated costs for labour, ICT, travel, contractor workforce, posting costs and supplier contracts. The project remains on cost and schedule.
Air Warfare Destroyer Program | SEA 4000 Phase 3 | 9103.73 | 7586.4462 | 376 | 226 | 226.558 | 198.8629 | -28 | The Chief of Navy in December 2018 declared HMAS Hobart had achieved Initial Operating Capability, after its successful Combat System Ship Qualification Trials in United States waters. The AWD Program is on schedule to achieve Provisional Acceptance of Ship 3 (Sydney) in February 2020. All project milestones were achieved. The financial variation is primarily due to invoices related to the Alliance Based Target Incentive Agreement and the Aegis Foreign Military Sales case being delayed for payment from June to July.
Maritime Operational Support Capability | SEA 1654 Phase 3 | 1070.6569 | 356.2429 | 280 | 286 | 216.5269 | 193.9499 | -23 | Nuship Supply is expecting harbour and sea trials planned for the period October to December 2019. The ship is then to be stored and prepared for delivery to Australia, with a sailing date planned for February 2020 from Spain. Nuship Stalwart workshop block pre-assembly is almost complete, and the ship is now being assembled at the slipway. It has achieved 85% of the block consolidation required for a planned launch for August 2019. The financial variation is primarily due to a delay in agreement and payment for essential Contract Change Proposals to the Prime Contract, relating to the procurement of Training and spares, as well as delays to other Government Furnished Material (GFM) procurement activities.
Offshore Patrol Vessel - Batch 1 | SEA 1180 Phase 1-A | 3724.2634 | 150.0226 | 274 | 221 | 209.9625 | 203.6045 | -6 | The keel laying ceremony for the first vessel, NUSHIP Arafura,was conducted in May 2019 at Osborne, SA. Construction commenced on the second vessel in June 2019, ahead of schedule. Civmec remains on track to commence the WA build of the third vessel in the second quarter of 2020. The financial variation is due to reduced requirements for Government Furnished Equipment and project support contracts.
Anzac Air Search Radar Replacement | SEA 1448 Phase 4B-A | 428.7253 | 132.9613 | 84 | 89 | 74.67 | 63.5718 | -11 | Delivery and installation of the First of Class Mission System into HMAS Arunta occurred as scheduled in early 2019. The integration and test program is progressing as anticipated prior to achieving Initial Materiel Release. The financial variation is primarily due to a second of class vessel experiencing delays in the sustainment led Anzac Midlife Capability Assurance Program. This has resulted in reprogramming the delivery of mission system two into 2019-20.
Pacific Patrol Boat Replacement | SEA 3036 Phase 1 | 504.0483 | 50.4319 | 72 | 71 | 69.9543 | 61.8673 | -8 | The Pacific Patrol Boat Replacement project will deliver 21 steel-hulled Guardian class Patrol Boats as part of Australia’s Pacific Maritime Security Program. In June 2019 the third Pacific Patrol Boat Replacement vessel was gifted to Tonga on schedule. The first was gifted to Papua New Guinea (November 2018), the second to Tuvalu (April 2019). The financial variation is primarily due to delays in infrastructure activities and reduced levels of expenditure against current Pacific Patrol Boats for disposal.
Future Frigate - Design and Construction | SEA 5000 Phase 1 | 6265.2195 | 263.9019 | 52 | 222 | 204.0718 | 153.1108 | -51 | During June 2018, the Government announced that ASC Shipbuilding, as a subsidiary of BAE Systems Australia, had been selected to build nine Hunter Class Frigates based on the Type 26 frigate design. In December 2018 the Commonwealth signed the Head Contract with ASC Shipbuilding. The Head Contract is the instrument that captures the agreement of both the Commonwealth and ASC Shipbuilding not just in relation to the initial scope for design and product ionisation, but also sets the terms and conditions for the build phase of the project. ASC Shipbuilding is a subsidiary of BAE Systems Australia, with a sovereign share owned by the Commonwealth. BAE Systems has committed to knowledge and data transfer to ASC Shipbuilding and its workforce. The Head Contract took effect from February 2019. Work has been underway to make the necessary changes to the baseline Type 26 design, as well as preparing the shipyard, work structures and systems in preparation for construction to begin with prototyping in 2020. Work on the first frigate will begin within 24 months of prototyping commencing, with steel on each subsequent ship being cut on an 24 month drumbeat. The first frigate is planned to be accepted in late 2020. The financial variation is primarily due to reprogramming of ramp-up activities following Government Approval and execution of the Head Contract. The reprogramming resulted in lower than planned expenditure against the Head Contract and parallel activities associated with Supply Chain Analysis and strategic support initiatives that were dependent on Contract signature. Legal expenses associated with establishing the Head Contract and associated Deeds were also less than expected for the size and complexity of negotiations. There were also invoice payments that were delayed from June to July.
Total -Top 30 Projects (Gross Plan) |  | 80011.5368 | 32094.8176 | 7382 | 7056 | 6672.3448 | 6227.1243 | -445
Other Approved Project Gross Plans |  | 51968.7978 | 30934.5357 | 1206 | 1953 | 1914.4992 | 1784.0559 | -130
Total - Approved Projects (Gross Plan) |  | 131980.3347 | 63029.3534 | 8588 | 9009 | 8586.844 | 8011.1803 | -576

## Table D.3
Web Table D.3: Top 30 acquisition projects - Government approvals and variations, 2018-19 |  |  | Total Government approval |  |  |  |  | Detail on 'Further Government approvals and variations'
Project name | Project number and phase | Initial project approval date | Original Government approval[1] $m | Price indexation variation $m | Exchange variation $m | Further Government approvals and variations[2] $m | Total current Government approval[3] $m | Real variations - second pass approval[4] $m | Scope[5] $m | Transfers[6] $m | Others[7] $m | Further Government approvals and variations $m
Air
New Air Combat Capability (NACC) | AIR 6000 Phase 2A/B | 30/11/2009 | 2751.593 | 351.035 | 2915.891 | 10504.125 | 16522.644 | 10,515(8) | 0 | -8.417 | -2.859 | 10504.125
Maritime Patrol and Response Aircraft System | AIR 7000 Phase 2 | 16/07/2007 | 144.099 | 20.531 | 481.0165 | 4730.1178 | 5375.7643 | 4,705(9) | 61.838 | -36.983 | -9.2e-05 | 4730.1178
Pilot Training System | AIR 5428 Phase 1 | 30/11/2009 | 7.766 | 0.213 | 53.4594 | 1189.0849 | 1250.5233 | 1189.2374 | 0 | -0.152 | -0.000572 | 1189.0849
Multi-Role Helicopter (MRH) | AIR 9000 Phase 2 | 22/04/2004 | 3.3 | 679.824 | -136.444 | 3224.3106 | 3770.9906 | 953.9 | 2,597 (10,11) | -326.444 | -0.000407 | 3224.3106
Airborne Early Warning & Control Interoperability Compliance Upgrade | AIR 5077 Phase 5A | 17/03/2015 | 1.5 | 0 | 35.7853 | 1155.4077 | 1192.693 | 1,020(12) | 103.405 | 31.282 | 0 | 1155.4077
EA-18G Growler Airborne Electronic Enabling | AIR 5349 Phase3 | 14/08/2012 | 1155.315 | 0 | 960.4764 | 1394.5235 | 3510.3149 | 303.2855 | 1,486(13) | -294.9 | -100 | 1394.5235
Future Naval Aviation Combat System (FNACS) | AIR 9000 Phase 8 | 10/07/2009 | 0.31 | 0.137 | 224.7056 | 2987.4438 | 3212.5965 | 3029.322 | 0 | -39.2031 | -2.675 | 2987.4438
Helicopter Aircrew Training System | AIR 9000 Phase 7 | 13/02/2007 | 13.6 | 2.429 | -4.5143 | 470.0647 | 481.5794 | 474.9685 | 0 | -3.2 | -1.7038 | 470.0647
Conversion of additional KC-30A to multi-role Tanker Transport | AIR 7403 Phase 3 | 24/06/2015 | 682 | 0 | 29.423 | 183 | 894.273 | 0 | 183 | 0 | 0 | 183
Battlefield Airlift - Caribou Replacement | AIR 8000 Phase 2 | 16/04/2012 | 1156.499 | 0 | 285.563 | -0.001028 | 1442.061 | 0 | -0.000514 | 0 | -0.000514 | -0.001028
Airborne Early Warning and Control Acquisition | AIR 5077 Phase 3 | 01/12/1997 | 2170.35 | 722.974 | -30.5295 | 1027.5419 | 3890.3363 | 1028 | 0 | 0 | 0 | 1027.5419
Joint
Battlefield Command Systems (Tranche 2) | LAND 200 Phase 2-A | 31/10/2017 | 0 | 0 | 30.8592 | 926.596 | 957.4552 | 926.596 | 0 | 0 | 0 | 926.596
Battlespace Communications System (Land) | JP 2072 Phase 2B | 25/10/2011 | 3.94 | 0 | 26.8506 | 911.8059 | 942.5966 | 911.806 | 0 | 0 | -5.9e-05 | 911.8059
Fixed Base Defence Air Traffic Management & Control System | AIR 5431 Phase 3 | 2011-11-21 | 731.404 | 0 | 3.7365 | 240.673 | 975.8135 | 0 | 247.48 | -6.807 | 0 | 240.673
ADF Identification Friend or Foe and Automatic Dependent Surveillance Broadcast | JNT 90 Phase 1 | 26/04/2012 | 15.867 | 0 | 3.0641 | 417.4216 | 436.3527 | 389.829 | 27.5926 | 0 | 0 | 417.4216
Satellite Ground Station (SGS) East and Wideband SATCOM Network Management System | JP 2008 Phase 5B2 | 26/04/2012 | 7.456 | 0 | 62.383 | 164.2006 | 234.0397 | 220.736 | 0 | -56.5356 | 0.000246 | 164.2006
Jindalee Operational Radar Network (JORN) Phase 6 | AIR 2025 Phase 6 | 21/01/2016 | 0 | 0 | -0.003744 | 1117.8558 | 1117.8558 | 1118 | 0 | 0 | 0 | 1117.8558
Fixed Base Defence Air Traffic Management & Control System | AIR 5431 Phase 2 | 20/01/2015 | 0 | 0 | 10.0398 | 191.977 | 202.0168 | 191.977 | 0 | 0 | 0 | 191.977
Land
Overlander - Medium Heavy Capability (MHC) Truck and Trailer components | LAND 121 Phase 3B | 2004-06-16 | 2572.541 | 0 | 145.107 | 682.2203 | 3399.8684 | 712.22 | 0 | -30 | 0.000331 | 682.2203
Overlander - Protected Mobility Vehicle - Light (Hawkei) | LAND 121 Phase 4 | 25/07/2008 | 1.767 | 0.364 | 34.2506 | 1943.1402 | 1979.5218 | 1,943(14) | 0 | 0 | 0 | 1943.1402
Night Fighting Equipment Replacement | LAND 53 Phase 1BR | 17/12/2013 | 2.995 | 0 | -17.7129 | 457.29 | 442.572 | 457.29 | 0 | 0 | 0 | 457.29
Chemical Biological Radiological Nuclear Defence (CBRND) | JP 2110 PH1 B | 22/03/2014 | 15.03 | 0 | 8.8542 | 229.52 | 253.4042 | 229.52 | 0 | 0 | 0 | 229.52
Soldier Enhancement Version 2 - Lethality | Land 125 Phase 3C | 24/01/2012 | 12.459 | 0 | -4.4912 | 455.2153 | 463.1832 | 455.2153 | 0 | 0 | 0 | 455.2153
Maritime
Future Submarine Design and Construction | SEA 1000 Phase 1B | 27/09/2016 | 1050.664 | 0 | 9.9343 | 4902.0617 | 5962.66 | 5002 | 0 | -100.2306 | 0 | 4902.0617
Air Warfare Destroyer Program | SEA 4000 Phase 3 | 19/06/2007 | 7,207(17) | 1173.244 | -366.4708 | 1089.5878 | 9103.73 | 1,199(15) | 0 | -109.9111 | 0 | 1089.5878
Maritime Operational Support Capability | SEA 1654 Phase 3 | 04/04/2014 | 13.239 | 0 | -3.3736 | 1060.4915 | 1070.3569 | 1060 | 0 | 0 | 0 | 1060.4915
Offshore Patrol Vessel - Batch 1 | SEA 1180 Phase 1-A | 28/02/2018 | 57.4 | 0 | 92.1615 | 3575.437 | 3724 | 3575.437 | 0 | 0 | 0 | 3575.437
Anzac Air Search Radar Replacement | SEA 1448 Phase 4B-A | 31/08/2017 | 3 | 0 | 0.96247 | 424.7628 | 428.7253 | 424.69 | 0.072792 | 0 | 0 | 424.7628
Pacific Patrol Boat Replacement | SEA 3036 Phase 1 | 29/08/2014 | 5.69 | 0 | -0.46472 | 498.823 | 504.0483 | 498 | 0 | 1.236 | 0 | 499
Future Frigate - Design and Construction | SEA 5000 Phase 1 | 02/06/2014 | 62.846 | 0 | 81.214 | 6121.1595 | 6265.2195 | 6,121(16) | 0 | 0 | 0 | 6121.1595
Total—top 30 projects (gross plan) |  |  | 19849.999 | 2950.751 | 4931.7328 | 52275.8579 | 80008.1945 | 48656.4297 | 4705.3879 | -980.2655 | -107.2389 | 52275.8579
Notes
1. Original approval represents the initial approved budget amount for the project.
2. Further Government Approvals represents all subsequent Government Approvals since the Original Government Approval when the project was initially endorsed, and approved budget variations.
3. The Total Current Government Approval amount may not add due to rounding.
4. Major capital equipment projects are managed in two stages: a definition stage, which is funded at first pass, and an acquisition stage, which is funded at second pass. There also may be multiple passes through Government in obtaining approvals for the various phases of a project.
5. The ‘Scope’ column shows any real cost increase or decrease provided to address a formal scope increase or decrease.
6. The ‘Transfers’ column reflects the total budget transfers to another project, Service Delivery Group, or to sustainment, with no net change to the existing project approval.
7. The ‘Others’ column shows all other real variations, such as budget price variations, reduction in a project's approved contingency budget, etc.
8. Second pass approval by Government to purchase an additional 58 F-35A Lightning II aircraft.
9. Second pass approval by Government for the purchase of 12 P-8A Poseidon aircraft and support systems.
10. Increase in scope associated with the acceleration of design development and planning activities.
11. Incorporation of Phase 4 – Black Hawk Upgrade/Replacement, and Phase 6 – Maritime Support Helicopter and Full Flight and Mission Simulator facilities, April 2006.
12. Second pass approval by Government for the completion of the interoperability compliance upgrades on the fleet of six Wedgetail aircraft, including ground systems and associated logistics support.
13. Acquisition of 12 new-build EA-18G Growler aircraft in lieu of modifying 12 existing F/A-18F Super Hornet aircraft to Growler configuration.
14. Second pass approval by Government for the acquisition of 1100 Hawkei Protected Mobility Vehicles - Light, and 1058 companion trailers.
15. Real Cost increase as agreed by Government.
16. Second pass approval by Government for ASC Shipbuilding to undertake design work, prototype activity and procure long lead items for the first three ships.
17. The SEA 4000 original Government approval amount includes both first and second pass approvals.

## Table D.4
Web Table D.4: Major acquisition projects closed in 2018-19
Project name * | Project number and phase | Project approval value $m | Total expenditure $m | Difference in project approval1 $m
Air
​Capability Assurance Program 2 ​Major | AIR05276CAP2 | 43.0481 | 43.0481 | 0
Hornet Upgrade Project​ Major​ | AIR05376PH2 | 1664.3246 | 1664.3246 | 0
New Air Combat Capability - ​Detailed Analysis and Acquisition Planning​ Major​ | AIR06000PH1B | 98.3762 | 98.3762 | 0
Joint Strike Fighter Project - SDD​ Major​ | AIR0JSFSDD | 200.307 | 200.307 | 0
Radio Frequency Sensor Sub-System​​ Major​​ | AIRJSFDD | 5 | 5 | 0
Joint
Joint Counter Improvised Explosive Device​ Major​​ | JNT00154PH1 | 75.3701 | 75.3701 | 0
Military Satellite Communications (MILSATCOM)​​ ​Major | JNT02008PH3E | 206.9123 | 206.9123 | 0
Military Satellite Capability - Wideband Terrestrial Terminals (WTT)​ ​Major | JNT02008PH3H | 41.4029 | 41.4029 | 0
​Next Generation Satellite Communications System ​​Major | JNT02008PH4 | 569.1118 | 569.1118 | 0
​Joint Direct Attack Munition Enhancement ​Major | JNT03027PH1 | 67.1466 | 58.6587 | 8.4878
Parakeet​ Major​ | JNT00065PH4 | 198.6236 | 198.6236 | 0
Parakeet​ Major​ | JNT00065PH6 | 105.4303 | 105.4303 | 0
Land
​Soldier Enhancement Version 2 - Survivability ​Major | LND00125PH3B | 177.7295 | 177.7295 | 0
Direct Fire Support Weapons​ Major​ | LND00040PH2 | 100.6734 | 100.6734 | 0
Replacement Aviation Fire Truck (RAFT) Capability Major | LND00998PH1 | 53.4306 | 53.413 | 0.017558
Maritime
Armidale Class Patrol Boats​ ​Major | SEA01444PH1 | 537.2032 | 537.2216 | -0.018388
Air Warfare Destroyer Combat System Integration and Risk Reduction Study ​Major | SEA04000PH1D | 11.476 | 11.476 | 0
Replacement Heavyweight Torpedo Major | SEA01429PH2 | 433.6679 | 337.5199 | 96.148
Navigation Display System​ Major​ | SEA01430PH2A | 46.0067 | 45.7227 | 0.284
​Collins Replacement Combat System​​ Major​ | SEA01439PH4A | 438.7837 | 438.7837 | 0
​Collins Class Sensor Improvements ​Major | SEA01439PH4B | 45.5085 | 45.1589 | 0.34962
Total—closed major projects |  | 3108.477 | 3003.2083 | 105.2687
Notes:
1. The savings primarily relate to unused contingency and unprogrammed funding within the project approval.
*One project has not been included in the table due to it's classified nature.

## Table D.5
Web Table D.5 - New major acquisition projects approved by Government in 2018–19
Project name | Project number and phase | Programmed estimate 2018–19 $m | Actual expenditure 2018–19 $m | Variation $m | Project summary and explanation of variation
|  | (a) | (b) | (b–a)
Air
Armed Medium Altitude Long Endurance Remotely Piloted Aircraft System | AIR 7003 Phase 1 | 2.4223 | 1.6045 | -1 | The project will deliver an Armed Medium Altitude Long Endurance Remotely Piloted Aircraft System providing the ADF with an airborne Intelligence, Surveillance, Reconnaissance and Electronic Warfare and precision Strike capability. The project is on track to meet Government approval in 2022. The project primarily achieved its budget.
Joint
Nulka Missile Decoy Enhancements | SEA 1397 Phase 5D | 30.378 | 30.7838 | 0 | This project is for procurement of next generation Nulka decoys and forms part of a suite of projects delivering increased capability for the Royal Australian Navy's Nulka anti-ship missile defence system. The project achieved its budget.
Protected Satellite Communications | SEA 1442 Phase 6 | 6.0282 | 2.8671 | -3 | This project is providing the ADF with a modern, secure and highly effective protected satellite communications capability, leveraging off the United States Advanced Extremely High Frequency Program. The project will deliver ground, space and control segments. The financial variation is primarily due to later than expected payment for the Milestone 1 contract deliverable requirement list.
Joint Electronic Warfare sub-Program | JP 9321 Phase 1 | 6.0073 | 2.8018 | -3 | This project is delivering capability to enable the coordinated Joint management of the Radio Frequency spectrum and the management of other ADF mission support data. This will include the automation of currently inefficient manual processes. The project will also deliver a force level automated direction finding capability. The financial variation is primarily due to later than expected undertaking of Joint Doctrine Update and proximity access studies.
Enhanced Defence High Frequency Communications System | JP 9101 Phase 1 | 4.51 | 2.0469 | -2 | This project will provide and assure the continued delivery and operation of a contemporary long range high frequency communications capability and integrate a new high frequency solution to deliver an advanced cyber secure capability. The financial variation is primarily due to later than expected initiation of tender evaluation activities.
Force Level Electronic Warfare System Land | LAND 555 Phase 6 | 2.189 | 0.81738 | -1 | This project will deliver land components of a force-level electronic warfare capability and will contribute to a joint system that can achieve high levels of information fusion and comprehensive planning across the joint force and Defence intelligence agencies. This will improve the ADF’s ability to control the electronic environment, and where necessary, deny or degrade the electronic systems of adversaries. The financial variation is primarily due to later than expected initiation of project support activities.
ESSM Upgrade and Inventory Replenishment | SEA 1352 Phase 1 | 26 | 55 | 29 | This project is upgrading the Evolved Sea Sparrow Missile point defence missile system in Frigates and Destroyers to counter the evolving regional Anti-Ship Missile threat. The financial variation is primarily due to earlier than expected payments for multi-national consortium activities.
Land
Medium and Heavy Vehicles | LAND 121 Phase 5B | 37.6035 | 57.5228 | 20 | This project will deliver 1044 vehicles, 872 modules and 812 trailers and completes the acquisition of medium heavy trucks and trailers that commenced under land 121 Phase 3B. The project is on schedule having met all planned deliverables for 2018-19. The financial variation is primarily due to an additional two milestones being delivered earlier than forecast.
Special OPS Cap Enhancement (GREYFIN) | LAND 1508 Phase 1 | 4.4316 | 3.9104 | -1 | The project will deliver defined capability enhancements to Special Operations Command units. The project primarily achieved its budget.
Integrated Soldier System | LAND 125 Phase 4.1 | 2.502 | 2.3491 | 0 | The project will deliver a broad range of capabilities that will refresh, augment and enhance equipment and training systems used by close combatants. The project achieved its budget.
Maritime
Future Frigate - Design and Construction | SEA 5000 Phase 1 | 204.0718 | 153.1108 | -51 | During June 2018, the Government announced that ASC Shipbuilding, as a subsidiary of BAE Systems Australia, had been selected to build nine Hunter Class Frigates based on the Type 26 frigate design. In December 2018 the Commonwealth signed the Head Contract with ASC Shipbuilding. The Head Contract is the instrument that captures the agreement of both the Commonwealth and ASC Shipbuilding not just in relation to the initial scope for design and product ionisation, but also sets the terms and conditions for the build phase of the project. ASC Shipbuilding is a subsidiary of BAE Systems Australia, with a sovereign share owned by the Commonwealth. BAE Systems has committed to knowledge and data transfer to ASC Shipbuilding and its workforce. The Head Contract took effect from February 2019. Work has been underway to make the necessary changes to the baseline Type 26 design, as well as preparing the shipyard, work structures and systems in preparation for construction to begin with prototyping in 2020. Work on the first frigate will begin within 24 months of prototyping commencing, with steel on each subsequent ship being cut on an 24 month drumbeat. The first frigate will be accepted in the late 2020. The financial variation is primarily due to delays in ramp-up activities following Government Approval, and execution of the Head Contract. Legal expenses associated with establishing the Head Contract and associated Deeds were also less than expected for the size and complexity of negotiations. There were also delays in invoice payments from June to July.
Navy Training Pipeline Simulation | SEA 3035 Phase 1 | 10.606 | 4.4095 | -6 | This project will deliver new and upgraded simulation training systems identical to those already in service within Navy. The financial variation is primarily due to delays in the delivery of the Canberra Class Virtual Combat Trainer.
Magnetic Treatment Facility | SEA 1350 Phase 2 | 0 | 0 | 0 | This project will replace the current Magnetic Treatment Facility (MTF) at HMAS Stirling which has exceeded its planned economic life. The proposed MTF capability will be an essential component of the RAN’s magnetic signature management of the Fleet and will support the RAN through to 2045. The project intends to deliver the objective requirement of providing a magnetic treatment capacity for platforms up to the size of the Canberra Class LHD and is currently in the process of developing a Request for Tender to be released in August 2019, for the Acquisition and Support of an Magnetic Treatment Facility Overrun capability solution at HMAS Stirling.
Total—new major projects |  | 310.7496 | 262.224 | -48.5256
Note: Double period (..) indicates ‘not zero, but rounded to zero’.

## Table D.6
Web Table D.6: Performance of capital facilities projects, 2018-19
Status key
Met—All targets for 2018-19 were met or executed.
Substantially met—Targets were mostly met and any issues were being managed.
Partially met—Some targets were met and any issues were being managed.
Not met—No or minimal progress was made against targets.
Project | State/Territory and electorate | Status | 2018-19 achievements
New Air Combat Capability (AIR 6000 NACC Phase 2A/B) | Various | Met | This project will provide new and upgraded facilities and infrastructure to support the introduction of the Joint Strike Fighter at RAAF Base Williamtown, Newcastle, NSW, and RAAF Base Tindal, Katherine, NT with support facilities and infrastructure provided at Defence Establishment Myambat, NSW and seven Forward Operating Bases. The project is scheduled for completion by mid-2020.
Enhanced Land Force (ELF) Stage 2 | Various | Partially met | This project will provide modern purpose-built facilities and supporting infrastructure for the 8th/9th Battalion, the Royal Australian Regiment and supporting elements of the Army's 7th Brigade at Gallipoli Barracks in Enoggera, Brisbane. The project includes the construction of new and refurbished accommodation and training facilities, as well as common use facilities and site infrastructure upgrades, at Enoggera and other Defence sites across four States and both mainland Territories. Facilities at Townsville, Singleton, Duntroon and Watsonia provide modern accommodation and supporting infrastructure for increased Army career training. In Sydney, at RAAF Bases Amberley and Edinburgh, and at nine other Defence Training Areas, new and refurbished facilities with site infrastructure upgrades will be provided for Army and joint enabling elements supporting the Enhanced Land Force capabilities. All works are complete with the exception of works at Cultana Training Area, including delivery of a wash point approved as part of Hardened Networked Army Phase 2 facilities project, which are scheduled for completion by early 2019.
Maritime Patrol Aircraft Replacement (AIR 7000 Phase 2B) | Various | Met | This project will provide new and upgraded facilities and infrastructure to support the introduction of the P-8A aircraft at RAAF Base Edinburgh, SA, RAAF Base Townsville, QLD, RAAF Base Pearce, WA and RAAF Base Darwin, NT, as well as additional explosive ordnance facilities at HMAS Stirling. The project is scheduled for completion by early 2020.
Hardened & Networked Army Phase 2, Facilities Project | Various | Partially met | This project will provide facilities and infrastructure to support the establishment of a mechanised battle group in the Edinburgh Defence Precinct. Some additional infrastructure has also been provided at Murray Bridge and will provide infrastructure at the Cultana Training Area. All works are complete with the exception of works at Cultana Training Area which is scheduled for completion by early 2019.
Larrakeyah Defence Precinct Redevelopment Program | NT - Solomon | Met | This program of works will upgrade critical base infrastructure, improve the working environment for Defence personnel including new facilities for North West Mobile Force (NORFORCE), and support future growth on Larrakeyah Defence Precinct. This project will also deliver a new wharf, fuel storage and refuelling capabilities to support Navy’s major surface combatant ships operating in the north of Australia. The project is scheduled for completion by mid 2023.
HMAS Cerberus Redevelopment | VIC - Flinders | Met | This project will provide engineering services upgrade, consolidation of Living In Accommodation and Mess Facilities, co-location of Clothing Store with Naval Store, School of Survivability and Ship Safety upgrade, Gym upgrade, Armoury, Explosive Ordnance and Weapons Storage Facility upgrade, and demolition. The project is scheduled for completion by mid 2025.
Air Traffic Control Complex Infrastructure Project and Fixed Base Defence Air Traffic Management and Control System (AIR 5431 Phase 2 and 3) | Various | Met | This project will provide facilities across 13 bases in support of replacement Air Traffic Management Surveillance, Command and Control Systems under AIR 5431 Phases 2 and 3, incorporating the replacement of aged and degraded Air Traffic Control Towers. The project is scheduled for completion by early 2023.
Battlefield Airlifter Facilities (AIR 8000 Phase 2) | QLD - Blair | Met | This project will provide facilities at RAAF Base Amberley, QLD to accommodate and support the operation of the new C-27J Battlefield Airlifter (BFA) aircraft. The project is scheduled for completion by mid 2019.
HMAS Stirling Redevelopment Stage 3A | WA - Brand | Met | This project will provide upgrades and refurbishment of existing critical shortfalls to infrastructure and facilities. The project is scheduled for completion by early 2020.
Growler Airborne Electronic Attack Capability Facilities (AIR 5349 Phase 3) | Various | Met | This project will provide necessary working accommodation, maintenance, warehousing and training facilities at RAAF Base Amberley, QLD to support the introduction of the Growler Airborne Electronic Attack Capability. The project is scheduled for completion by mid 2020.
Pilot Training System Facilities (AIR 5428 Phase 1) | Various | Met | The project will provide fit-for-purpose facilities to support the modern joint training system being delivered by the AIR5428-1 Capability Project, with the facilities planned to be delivered at RAAF Base East Sale, VIC, RAAF Base Pearce and Gingin, WA, RAAF Base Williamtown, NSW and RAAF Base Edinburgh, SA. The project is scheduled for completion in late 2020.
Garden Island (East) Critical Infrastructure Recovery (CIRP) - Stage 2 | NSW - Sydney | Met | This project will provide upgraded wharves and engineering services to address condition, capacity and compliance issues on the Cruiser Wharf at Garden Island (East), Sydney, NSW. This project is scheduled for completion by late 2023.
LAND 121 Stage 2A | Various | Met | This project will provide facilities across nine bases to sustain the B-vehicle fleet IAW the Basis of Issue for Army, RAAF and JLC. These facilities will maintain (workshops and repair parts storage), support (fuel points, loading ramps, wash points and weigh bridges) and sustain (shelters and hardstand) the vehicles from vehicle acquisition Phase 3A (G-Wagon), Phase 3B (Light/Light Weight and Medium/Heavy) and Phase 4 (Protected Mobility Vehicles Light). The project is scheduled for completion by early 2020.
RAAF Base Williamtown Redevelopment Stage 2 | NSW - Paterson | Met | This project will sustain and improve the functionality and capability of RAAF Base Williamtown, NSW, including upgrades or replacement of critical ageing infrastructure to meet future requirements. The project is scheduled for completion by late 2021.
Maritime Operational Support Capability Facilities | Various | Met | This project will provide new and upgraded facilities and infrastructure to support the introduction of a single class of Auxiliary Oiler Replenishment vessels, being provided under SEA 1654 Phase 3 MOSC Project. This project is scheduled for completion by late 2020.
Explosive Ordnance Logistics Reform Program | Various | Met | This project will address explosive ordnance storage capacity shortfalls through delivery of new and enhanced explosive ordnance facilities at 12 Defence sites. The project is scheduled for completion by late 2020.
Campbell Barracks Redevelopment | WA - Curtin | Substantially met | This project will provide a new Headquarters for the Special Air Services Regiment, communications facilities, working accommodation, storage facilities and supporting site infrastructure at Campbell Barracks, WA. The project is scheduled for completion by early 2019.
C-17 Maintenance Facility, Aircraft Apron and Associated Infrastructure (AIR 8000 Phase 3) | QLD - Blair | Met | This project will provide a maintenance facility, working accommodation, an aircraft apron and associated facilities at RAAF Base Amberley. This project is scheduled for completion by late 2019.
Garden Island (East) Critical Infrastructure Recovery (CIRP) - Stage 1 | NSW - Sydney | Met | This project will address critical structural, condition and engineering services risks on the Cruiser Wharf at Garden Island (East), Sydney, NSW. The project is scheduled for completion by early 2022.
Joint Health Command Garrison Facilities Upgrade | Various | Met | This project will provide fit for purpose, contemporary Garrison Health Facilities at 13 sites across Australia. The project is scheduled for completion by late 2020.
Airfield Capital Works P0007 (East Sale, Pearce, Gingin and Oakey) | Various | Met | This project will provide major maintenance to aircraft pavement and aeronautical ground lighting to RAAF Bases Pearce, Gingin, East Sale and Army Aviation Centre Oakey. The project is scheduled for completion by late 2020.
Defence Terrestrial Communications Network Facilities Upgrade (JP 2047 Phase 3) | Various | Substantially met | This project will provide upgraded and new communications infrastructure and supporting facilities at multiple Defence owned and leased sites across Australia. The project will support the introduction into service of the new Defence Terrestrial Communications Network. The project is scheduled for completion by early 2019.
Defence Force School of Signals (DFSS) Redevelopment Project, Watsonia | Various | Met | This project will provide working accommodation at Simpson barracks, VIC to support DFSS Maritime Communications and Information Systems Wing at HMAS Cerberus. Construction is scheduled to be complete by early 2020.
Airfield Capital Works P0006 (Curtin, Tindal and Townsville) | Various | Met | This project will resurface asphalt pavement and replace airfield lighting at RAAF Base Curtin, WA, RAAF Base Tindal, NT and RAAF Base Townsville, QLD. The project is scheduled for completion by mid 2022.
Space Surveillance Telescope (JP 3029 Phase 2) | WA - Durack | Met | This project will provide facilities and infrastructure to support the operations of the Space Surveillance Telescope, which will enable ADF space surveillance capability, enhanced global surveillance capability, and an increased ability to track space debris. The project is scheduled for completion by late 2019.
Russell Office Precinct Upgrade R5 and R6 Midlife Upgrade | ACT- Canberra | Met | The project will provide essential building and engineering services upgrades to extend the life of Russell Buildings R5 and R6. The project is scheduled for completion by mid-2020.
Delamere Range Facilities Redevelopment | NT - Lingiari | Substantially met | This project will redevelop key range facilities and infrastructure to enable Growler and Mobile Threat Training Emitter Systems capability at Delamere Air Weapons Range, NT. The project is scheduled for completion by early 2019.
Land 17 Phase 1B/1C | Various | Met | This project will provide facilities at eight Defence establishments to provide the necessary working, storage, maintenance and training facilities to support the additional Lightweight Towed Howitzer and simulation capability being acquired under LAND 17 Phase 1B/1C. The project is scheduled for completion by late 2019.
Jindalee Operational Radar Networks (JORN) Phase 6 Facilities Project | Various | Met | This project will provide new facilities and infrastructure to support the mid-life upgrade of the JORN capability under AIR2025Ph6, with priority works at the JORN Radar 3 Receive (Mount Everard) and Transmit (Harts Range) sites near Alice Springs, NT. The project is scheduled for completion by late 2020.
REDFIN Infrastructure (JP 2097 Phase 1B) | Various | Met | This project will provide facilities for the Special Operations Vehicle fleet to support mobility and communications for Special Operations Forces. The project is scheduled for completion by late 2019.
Woomera Range Remediation Facilities (AIR 3024 Phase 1) | SA - Grey | Partially met | This facilities project will provide new and upgraded facilities and infrastructure that are capable of facilitating the operation of a new range safety and control system at Woomera, SA. The project is scheduled for completion by early 2019.
Replacement Aviation Refuelling Vehicles Infrastructure (JP157 Phase 1) | Various | Met | This project will provide new and upgraded facilities to support a new fleet of aviation refuelling vehicles at 15 locations. The project is scheduled for completion by late 2019.
Puckapunyal Military Area High Voltage Upgrade | VIC - Nicholls | Substantially met | This project will provide an essential upgrade to the High Voltage power supply and reticulation network at the Puckapunyal Military Area, VIC. The project is scheduled for completion in early 2019.
Electronic Warfare Operational Support (JP500 Phase 2) | SA - Wakefield | Met | This project will provide facilities to support Joint Project 500 Phase 2A – Electronic Warfare Operational Support, at the Edinburgh Defence Precinct, SA. Construction is complete and the project is currently in the Defects Liability Period.
LAND 155 Enhanced Gap Crossing Capability | Various | Met | This project will replace current bridging capability with the acquisition of new Military Off The Shelf bridging equipment. Construction is complete and the project is currently in the Defects Liability Period.
LAND 2110 Phase 1B -Chemical, Biological, Radiological, Nuclear Defence (CBRND) Facilities | Various | Not met | This project will provide new and refurbished facilities including training and storage facilities at 14 Defence sites to support Australian Defence Force CBRND activities. Construction is scheduled to commence in mid 2019 and is scheduled for completion by late 2019.
HMAS Moreton Unit Relocation | QLD - Griffith | Met | This project will ensure that Navy’s operational and administrative functions are retained after the partial disposal of surplus Defence land at Bulimba Barracks. The project also seeks to construct new facilities and services on the remaining portion of the site to replace those functions that will be displaced due to the partial disposal of the site. The project is scheduled for completion by mid 2019.

## Table D.7
Web table D.7: Major Defence establishments and bases
Establishment and base | Federal electorate | Location
Australian Capital Territory (and Jervis Bay Territory)
Anzac Park West | Canberra | Parkes
Australian Defence College | Bean | Weston
Australian Defence Force Academy (ADFA) | Canberra | Canberra
Beecroft Training Range | Fenner | Jervis Bay Territory
Brindabella Park | Canberra | Canberra Airport
Campbell Park Offices | Canberra | Campbell
Fairbairn | Canberra | Canberra Airport
HMAS Creswell | Fenner | Jervis Bay Territory
HMAS Harman | Bean | Canberra
Royal Military College | Canberra | Duntroon
Russell Offices | Canberra | Russell
New South Wales
Blamey Barracks | Riverina | Kapooka
Defence Establishment Orchard Hills | Lindsay | Orchard Hills
Defence Plaza Sydney | Sydney | Sydney
Garden Island Defence Precinct | Sydney | Sydney
General John Baker Complex | Eden–Monaro | Bungendore
HMAS Albatross | Gilmore | Nowra
HMAS Penguin | Warringah | Balmoral
HMAS Waterhen | North Sydney | Waverton
HMAS Watson | Wentworth | Watsons Bay
Liverpool Military Area | Hughes | Liverpool
Lone Pine Barracks | Hunter | Singleton
RAAF Base Glenbrook | Macquarie | Glenbrook
RAAF Base Richmond | Macquarie | Richmond
RAAF Base Wagga | Riverina | Wagga Wagga
RAAF Base Williamtown | Paterson | Williamtown
Randwick Barracks | Kingsford Smith | Randwick
Victoria Barracks, Sydney | Wentworth | Paddington
Northern Territory
Bradshaw Field Training Area | Lingiari | Katherine
Defence Establishment Berrimah | Solomon | Coonawarra
Delamere Range Facility | Lingiari | Katherine
Joint Defence Facility - Pine Gap | Lingiari | Alice Springs
Kangaroo Flat Training Area | Solomon | Winnellie
Larrakeyah Defence Precinct | Solomon | Larrakeyah
Markmanship Training Range (MTR) Range Control | Lingiari | Palmerston
Mount Bundey Training Area | Lingiari | Darwin
RAAF Base Darwin | Solomon | Winnellie
RAAF Base Tindal | Lingiari | Katherine
Robertson Barracks | Lingiari | Palmerston
Robertson Barracks Close Training Area | Lingiari | Darwin
Shoal Bay Receiving Station | Lingiari | Palmerston
Queensland
Borneo Barracks | Groom | Cabarlah
Canungra Training Area (CTA) | Wright | Canungra
Cowley Beach Training Area (CBTA) | Kennedy | Cawley Beach
Damascus Barracks, Meeandah | Lilley | Brisbane
Enoggera Close Training Area | Ryan | Enoggera
Gallipoli Barracks | Ryan | Enoggera
Greenbank Training Area | Wright | Brisbane
HMAS Cairns | Leichhardt | Portsmith
HMAS Moreton | Griffith | Bulimba
Kokoda Barracks | Wright | Canungra
Lavarack Barracks | Herbert | Townsville
Mt Stuart Training Area (MSTA) | Herbert | Townsville
New Defence Training Area, Greenvale | Kennedy | Greenvale
Porton Barracks | Kennedy | Edmonton
RAAF Base Amberley | Blair | Amberley
RAAF Base Scherger | Leichhardt | Weipa
RAAF Base Townsville | Herbert | Townsville
Ross Island Barracks | Herbert | Townsville
Sarpeye Barracks Thursday Island | Leichhardt | Weipa
Shoalwater Bay Training Area (SWBTA) | Capricornia | Rockhampton
Swartz Barracks (Army Aviation Centre Oakey) | Groom | Oakey
Townsville Field Training Area (TFTA) | Kennedy | Townsville
Tully Training Area (TTA) | Kennedy | Townsville
Victoria Barracks | Brisbane | Brisbane
Wide Bay Training Area | Wide Bay | Brisbane
South Australia
Cultana Training Area (CUTA) | Grey | Port Augusta
Edinburgh Defence Precinct | Spence | Edinburgh
Hampstead Barracks | Adelaide | Greenacres
Keswick Barracks | Adelaide | Keswick
Murray Bridge Training Area (MUTA) | Barker | Adelaide
Proof and Experimental Establishment Port Wakefield | Grey | Port Wakefield
RAAF Base Woomera | Grey | Murray Bridge
Warradale Barracks | Boothby | Adelaide
Woodside Barracks | Mayo | Woodside
Tasmania
ADF Cadets | Bass | Launceston/Georgetown
Anglesea Barracks | Clark | Hobart
Australian Defence Cadet Facilities | Lyons | Bridgewater
Buckland Military Training Area | Lyons | Tasmania
Burnie Depot (Wivenhoe) | Braddon | Burnie
Defence Science and Technology Group (DSTG) Scottsdale | Bass | Scottsdale
Derwent Barracks | Clark | Dowsing Point
Devonport Depot (Kokoda Barracks) | Braddon | Devenport
Fort Direction | Franklin | Tasmania
Navy Cadet Training Ships (TS) | Clark | Hobart
Patterson Barracks | Bass | Launceston
Stony Head Military Training Area | Bass | Launceston
Warrane Depot | Franklin | Tasmania
Youngtown Depot | Bass | Tasmania
Victoria
AGO Geospatial Analysis Centre | Bendigo | Bendigo
Albury Wodonga Military Area | Indi | Albury / Wodonga
Benalla Munitions Facility | Indi | Benalla
Defence Plaza Melbourne | Melbourne | Melbourne
Defence Science and Technology Group (DSTG) Fishermans Bend | Macnamara | Fishermans Bend
HMAS Cerberus | Flinders | Crib Point
Land Engineering Agency (LEA) Proving Ground Monegeetta | McEwen | Melbourne
Proof and Experimental Establishment Graytown | Nicholls | Graytown
Puckapunyal Military Area | Nicholls | Seymour
RAAF Base East Sale | Gippsland | East Sale
RAAF Base Williams (Laverton) | Lalor | Laverton
RAAF Base Point Cook | Lalor | Point Cook
Simpson Barracks | Jagajaga | Macleod
Victoria Barracks | Macnamara | Southbank
Western Australia
Australian Defence Satellite Comms Station | Durack | Kojarena
Bindoon Training Area | Pearce | Bullsbrook
Campbell Barracks | Curtin | Swanbourne
HMAS Stirling | Brand | Garden Island
Irwin Barracks | Curtin | Karrakatta
Lancelin Training Area | Pearce | Bullsbrook
Leeuwin Barracks | Fremantle | Fremantle East
Muchea Training Area | Pearce | Bullsbrook
Naval Comms Station, Harold E Holt | Durack | Exmouth
Northam Training Camp | Pearce | Northam
Palmer Barracks | Hasluck | Perth
RAAF Base Curtin | Durack | Derby
RAAF Base Learmonth | Durack | Learmonth
RAAF Base Pearce | Pearce | Bullsbrook
Taylor Barracks | Durack | Karratha

## Table D.8
Web Table D.8: Status of capital facilities projects for consideration and approval by the Parliamentary Standing Committee on Public Works in 2018-19
Project | State/territory and electorate | PWC Referral Date[1] | PWC Hearing Date[1&2] | Parliamentary Approval Date[1]
Major projects foreshadowed for consideration and approval in 2018-19 [7]
LAND 2110 Phase 1B – Chemical, Biological, Radiological and Nuclear Defence Capability Facilities | Multiple | 2018-05-10 | 2018-07-30 | 2018-08-23
AIR 2025 Phase 6 Jindalee Operational Radar Network Facilities | Multiple | 2018-05-24 | 2018-07-30 | 2018-08-23
Point Wilson Waterside Infrastructure Redevelopment | VIC - Corio [6] | 2018-06-28 | 2018-08-24 | Mid 2019
LAND 200 Tranche 2 – Battlefield Communication System Facilities | Multiple | 2018-08-16 | 2018-11-09 | 2019-02-13
Naval Guided Weapons Maintenance Facilities Project | NSW - Lindsay | 2018-08-16 | 2018-11-09 | 2019-02-14
LAND 4502 Phase 1 – Additional Chinook Capability Facilities | QLD - Herbert | 2018-08-23 | 2018-11-09 | 2019-02-13
Defence High Performance Computing Centre | SA - Spence [6] | 2018-09-13 | 2018-10-29 | 2018-11-09
Shoalwater Bay Training Area Remediation Project[3] | QLD - Capricornia | Mid 2019 | Mid 2019 | Late 2019
Navy Capability Infrastructure Sub-program (combining SEA 5000 Phase 1 Future Frigates and SEA 1180 Phase 1 Offshore Patrol Vessels Project Batch 1)[3] | Multiple | Mid 2019 | Late 2019 | Late 2019
HMAS Watson Redevelopment[3] | NSW - Wentworth | Mid 2019 | Late 2019 | Late 2019
AIR 555 Phase 1 Airborne Intelligence, Surveillance, Reconnaissance, Electronic Warfare Facilities Project [3] | Multiple | Late 2019 | Late 2019 | Late 2019
AlR 7000 Phase 1B Remotely Piloted Aircraft System Facilities Project [3] | Multiple | Late 2019 | Late 2019 | Late 2019
Facility Upgrade Australian Defence Simulation and Training Centre & JP 9711 Phase 1 Core Simulation Capability Facilities[3] | ACT - Bean [6] | Late 2019 | Early 2020 | Early 2020
KC-30A Multi Role Tanker Airfield Upgrades, RAAF Base Learmonth[3] | WA - Durack | Early 2022 | Early 2022 | Mid 2022
Project | State/territory and electorate | Date of PWC Notification Approval[1]
Medium projects foreshadowed for consideration and approval in 2018-19
Building 106 Extensions and Alterations, Environmental Test Facility Proof and Experimental Establishment Project | SA - Spence [6] | 2018-05-10
Australian Government Security Vetting Agency Fitout Project[4] | QLD - Brisbane | 2018-09-20
Robertson Barracks Close Training Area Post Acquisition Works Project | NT - Lingiari [6] | 2018-10-18
Walker House Fit-out, Canberra, Project[4] | ACT - Canberra | 2018-12-06
United States Force Posture Initiative Marine Rotational Force Darwin Modular Accommodation RAAF Base Darwin Project | NT - Solomon | 2019-04-04
Facilities for LAND 154 Phase 2 Stage 1 Joint Counter Improvised Explosive Device Capability[5] | Multiple | Late 2019
2 CER Compensatory Hardstand Project[5] | QLD - Ryan | Late 2019
Facilities for SEA 1442 Phase 6 Collins Satellite Communication[5] | Multiple | Late 2019
Sewerage Treatment Plant | Multiple | Late 2020
Notes:
1. Full dates confirm actual referral, hearing, Parliamentary approval or PWC Notification approval dates. Forecasted dates are shown as “Early”, “Mid”, “Late”.
2. Hearing dates are subject to the Public Works Committee’s consideration and agreement.
3. These projects were reported in the 2018-19 PBS/PAES as being foreshadowed for approval in FY 2018-19, however approval has slipped to FY 2019-20.
4. These projects were not reported in the PBS or PAES. The Committee approved them in FY 2018-19 to be delivered as medium works.
5. These projects were reported in the 2018-19 PBS/PAES as being foreshadowed to be notified to the Public Works Committee in FY 2018-19, however notifications have slipped to FY 2019-20.
6. Electorate change due to boundary change/renaming or incorrect reporting in the 2018-19 PBS/PAES.
7. The Puckapunyal Health and Wellbeing Centre; Puckapunyal Military Area Mid Term Refresh; SEA 1397 Phase 5D Nulka Assembly Maintenance Facilities; Singleton Mid Term Refresh; LAND 555 Phase 6 – Force Level Electronic Warfare, Signals Intelligence & Vehicles were projects that were reported in the PBS as Major Projects foreshadowed for referral to the Public Works Committee in FY 2018-19, however have slipped to future financial years. In March 2019 the financial threshold for referral of Defence projects to the Public Works Committee was increased from $15 million to $75 million. As a result, because these projects are valued between $15 million and $75 million they have been transferred to the PWC Medium Works Program:

## Table D.9
Web Table D.9: Approved Major Capital Facilities Projects, by State/Territory and Federal Electorate
Project | State/Territory, and Federal Electorate | Total Estimated Expenditure $m | Cumulative Expenditure to 30 June 2018 $m | 2018-19 Budget Estimate $m | 2018-19 Revised Estimate $m | 2018-19 Actual Expenditure $m
New Air Combat Capability (AIR 6000 NACC Phase 2A/B) [1]
RAAF Tindal | NT - Lingiari |  | 243.145 | 128.7 | 174.3 | 200.6146
RAAF Base Edinburgh | SA - Spence |  | 0 | 0 | 0 | 0
| WA - Durack |  | 0 | 0.1 | 0 | 0
RAAF Curtin | WA - Durack |  | 0 | 0 | 0 | 0
RAAF Townsville | QLD - Herbert |  | 0 | 0 | 0 | 0
Defence Establishment Myambat | NSW - Hunter |  | 0 | 3.3 | 0 | 1.0091
RAAF Williamtown | NSW - Paterson |  | 751.2651 | 93.8 | 92.1 | 88.9604
RAAF Darwin | NT - Solomon |  | 0 | 0.1 | 0 | 0
RAAF Pearce | WA - Pearce |  | 0 | 0 | 0 | 0
RAAF Scherger | QLD - Leichhardt |  | 0 | 0 | 0 | 0
Total |  | 1485.8 | 994.41 | 226 | 266.4 | 290.584
Enhanced Land Force (ELF) Stage 2[1]
Lone Pine Barracks | NSW - Hunter |  | 0 | 0 | 0 | 0
Singleton Military Area | NSW - Hunter |  | 115.8338 | 0 | 0 | 0
Puckapunyal Training Area | VIC - Nicholls [5] |  | 11.7105 | 0 | 0 | 0.085587
Simpson Barracks, Watsonia | VIC - Jagajaga |  | 20.156 | 0 | 0 | 0
RAAF Amberley | QLD - Blair |  | 9.6338 | 0 | 0 | 0
Lavarack Barracks, Townsville | QLD - Herbert |  | 61.9875 | 0 | 0 | 0
Townsville Training Area | QLD - Kennedy |  | 3.949 | 0 | 0 | 0
Greenbank Training Area | QLD - Rankin |  | 120.6793 | 0 | 0 | 0
Gallipoli Barracks, Enoggera | QLD - Ryan |  | 828.9198 | 0 | 0 | 0
Wide Bay Training Area | QLD - Wide Bay |  | 78.2822 | 0 | 0 | 0
Mt Stuart | QLD - Kennedy |  | 4.0966 | 0 | 0 | 0
Kokoda Barracks, Canungra | QLD - Wright |  | 71.8418 | 0 | 0 | 0
Cultana Training Area | SA - Grey |  | 42.0568 | 15.2 | 27.2 | 19.7796
RAAF Edinburgh | SA - Spence [5] |  | 34.5423 | 0 | 0 | 0
Royal Military College (RMC) | ACT - Canberra |  | 9.0149 | 0 | 0 | 0
Majura Field Training Area | ACT - Fraser |  | 13.3529 | 0 | 0 | 0
Total |  | 1457.8 | 1426.0572 | 15.2 | 27.2 | 19.8652
Maritime Patrol Aircraft Replacement (AIR 7000 Phase 2B)[1]
HMAS Stirling | WA - Brand |  | 4.2675 | 1.8 | 0 | 0
RAAF Edinburgh | SA - Spence [5] |  | 301.8787 | 57.9 | 138.8 | 108.4067
RAAF Townsville | QLD - Herbert |  | 0 | 0 | 0 | 0
RAAF Pearce | WA - Pearce |  | 0 | 57.1 | 0 | 0
RAAF Darwin | NT - Solomon |  | 0 | 75.6 | 0 | 3.0831
Total |  | 707.9 | 306.1463 | 192.4 | 138.8 | 111.4897
Hardened & Networked Army (HNA) Phase 2 [1]
RAAF Edinburgh | SA - Spence [5] |  | 489.3568 | 0 | 0 | 7.122
Murray Bridge | SA - Barker |  | 0 | 0 | 0 | 0
Cultana Training Area | SA - Grey |  | 0 | 1.3 | 7.9 | 0
Total |  | 597.4 | 489.3568 | 1.3 | 7.9 | 7.122
Larrakeyah Defence Precinct Redevelopment Program
Larrakeyah Defence Precinct | NT - Solomon | 495.6 | 0 | 0 | 22.7 | 24.9488
HMAS Cerberus Redevelopment[7]
HMAS Cerberus | VIC - Flinders | 465.6 | 28.7844 | 100 | 90 | 111.3255
Air Traffic Control Complex Infrastructure Project and Fixed Base Defence Air Traffic Management and Control System (AIR 5431 Phases 2 and 3) [1]
RAAF Tindal | NT - Lingiari |  | 40.1806 | 7.9 | 5.6 | 4.9997
RAAF Amberley | QLD - Blair |  | 44.4714 | 1.9 | 6.4 | 4.5584
RAAF Woomera | SA - Grey |  | 0.90399 | 5.1 | 0 | 0
HMAS Albatross | NSW - Gilmore |  | 5.1279 | 5.9 | 11.6 | 11.7681
RAAF Richmond | NSW - Macquarie [6] |  | 20.4313 | 8.6 | 8 | 7.3663
Army Aviation Centre Oakey | QLD - Groom |  | 21.2985 | 9.7 | 14.9 | 14.5269
RAAF East Sale | VIC - Gippsland |  | 8.9597 | 0.3 | 0.7 | 0.71148
RAAF Edinburgh | SA - Spence [5] |  | 7.0167 | 0.5 | 0.5 | 0.54098
RAAF Williamtown | NSW - Paterson |  | 29.8151 | 13.4 | 14.6 | 13.7889
RAAF Townsville | QLD - Herbert |  | 31.7089 | 11.2 | 8.7 | 6.616
RAAF Gingin | WA - Pearce |  | 6.5504 | 2.4 | 1.2 | 0.77267
RAAF Darwin | NT - Solomon |  | 9.4389 | 19.7 | 11.5 | 6.3836
RAAF Pearce | WA - Pearce |  | 25.3187 | 10.2 | 8.5 | 7.7467
Total |  | 409.9 | 251.222 | 96.8 | 92.2 | 79.7797
Growler Airborne Electronic Attack Capability Facilities (AIR 5349 Phase 3)[1][7]
Delamere Weapons Range | NT - Lingiari |  | 37.2909 | 16.4 | 16.4 | 22.1219
RAAF Amberley | QLD - Blair |  | 161.8972 | 77.6 | 71.2 | 96.0412
Total |  | 388.6 | 199.1881 | 94 | 87.6 | 118.1631
Battlefield Airlifter Facilities (AIR 8000 Phase 2)
RAAF Amberley | QLD - Blair | 370.379 | 237.0061 | 80.8 | 112.2 | 100.6574
HMAS Stirling Redevelopment Stage 3A
HMAS Stirling, Rockingham | WA - Brand | 366.8 | 63.9428 | 154.6 | 142.5 | 178.8069
Pilot Training System Facilities (AIR 5428 Phase 1)[1]
RAAF East Sale | VIC - Gippsland |  | 155.5027 | 17.8 | 42.8 | 18.9187
RAAF Williamtown | NSW - Paterson |  | 0 | 1 | 0 | 0
RAAF Edinburgh | SA - Spence [5] |  | 0 | 3.7 | 0 | 0
RAAF Pearce | WA - Pearce |  | 77.7289 | 7.4 | 7.4 | 13.514
RAAF Gingin | WA - Pearce |  | 9.2577 | 2.5 | 2.5 | 0.085087
Total |  | 329.8 | 242.4893 | 32.4 | 52.7 | 32.5177
Garden Island Critical Infrastructure Recovery - Stage 2
Garden Island Defence Precinct | NSW - Sydney | 286.5 | 0 | 0 | 18 | 8.0015
LAND 121 Stage 2A[1]
Robertson Barracks | NT - Lingiari |  | 0.60448 | 0.5 | 0.5 | 0.39594
Campbell Barracks | WA - Curtin |  | 1.5735 | 5.8 | 5.8 | 6.4157
Holsworthy Barracks | NSW - Hughes |  | 1.3243 |  | 0 | 0.56754
Lavarack Barracks | QLD - Herbert |  | 106.1443 | 24.8 | 23 | 20.5087
Puckapunyal Training Area | VIC - McEwan Nicholls [5] |  | 20.7643 | 1.2 | 2.1 | 2.6516
RAAF Williamtown | NSW - Paterson |  | 12.7063 | 1.4 | 0.1 | 0.044705
RAAF Darwin | NT - Solomon |  | 2.4813 | 0 | 0 | 0
RAAF Edinburgh | SA - Spence [5] |  | 8.8635 | 0 | 0 | 0.048978
Gallipoli Barracks | QLD - Ryan |  | 41.0364 | 16.9 | 11.4 | 12.6871
Total |  | 276.5 | 195.4982 | 50.6 | 42.9 | 43.3203
RAAF Base Williamtown Redevelopment Stage 2
RAAF Williamtown | NSW - Paterson | 274 | 100.2703 | 83.3 | 97.1 | 100.923
Explosive Ordnance Logistics Reform Program[1]
Twofold Bay | NSW - Eden-Monaro |  | 0.015754 | 3.1 | 3.1 | 7.2792
HMAS Stirling | WA - Brand |  | 0.052345 | 10.3 | 10.3 | 8.5722
RAAF Amberley | QLD - Blair |  | 0.056919 | 11.2 | 11.2 | 20.9333
Point Wilson | VIC - Corio |  | 0 | 0 | 0 | 0
HMAS Cerberus | VIC - Flinders |  | 0.04523 | 8.7 | 8.9 | 13.1039
Myambat | NSW - Hunter |  | 0.068099 | 25.9 | 13.4 | 19.591
Fort Direction | TAS - Franklin |  | 0.013721 | 2.5 | 2.7 | 3.121
Mt Stuart | QLD - Kennedy |  | 0.05082 | 10 | 10 | 9.7305
RAAF Williamtown | NSW - Paterson |  | 0 | 0 | 0 | 0
RAAF Darwin | NT - Solomon |  | 0.069624 | 13.7 | 13.7 | 18.3676
RAAF Edinburgh | SA - Spence [5] |  | 0.074198 | 14.6 | 14.6 | 10.4951
Mangalore | VIC - Nicholls [5] |  | 0.067591 | 13.3 | 13.3 | 4.0416
Total |  | 230.851 | 0.5143 | 113.3 | 101.2 | 115.2355
Campbell Barracks Redevelopment
Campbell Barracks | WA - Curtin | 230.4 | 192.0197 | 31.4 | 38.2 | 31.7399
Maritime Operational Support Capability Facilities [1]
HMAS Stirling | WA - Brand |  | 1.5935 | 12 | 5.4 | 0.81815
Randwick Barracks | NSW - Kingsford Smith |  | 6.2266 | 25.1 | 21.1 | 3.1969
Garden Island Defence Precinct | NSW - Sydney |  | 0.02951 | 0.1 | 0.1 | 0.015151
Total |  | 220.5 | 7.8497 | 37.2 | 26.6 | 4.0302
C-17 Maintenance Facility, Aircraft Apron and Associated Infrastructure (AIR 8000 Phase 3)
RAAF Amberley | QLD - Blair | 219.39 | 115.8112 | 59.8 | 43.8 | 57.6709
Garden Island Critical Infrastructure Recovery - Stage 1
Garden Island Defence Precinct | NSW - Sydney | 213.41 | 8.9717 | 67.4 | 38.4 | 31.6623
Joint Health Command Garrison Facilities Upgrade
Robertson Barracks | NT - Lingiari |  | 0.00036804 | 8 | 3 | 0.56587
Army Aviation Centre Oakey | QLD - Groom |  | 0 | 0 | 0 | 0
Holsworthy Barracks | NSW - Hughes |  | 0.00049072 | 6.4 | 4 | 2.8781
Albury-Wodonga | VIC - Indi |  | 0.0012268 | 19 | 10 | 7.0279
Royal Military College (RMC) | ACT - Canberra |  | 0.0012268 | 20 | 10 | 4.282
Simpson Barracks | VIC - Jagajaga |  | 0 | 1.6 | 0 | 0
RAAF Townsville | QLD - Herbert |  | 0 | 0 | 0 | 0
Puckapunyal Training Area | VIC - Nicholls [5] |  | 0 | 3.3 | 0 | 0
Larrakeyah Barracks | NT - Solomon |  | 0.00024536 | 17.7 | 2 | 0.74117
RAAF Pearce | WA - Pearce |  | 0.00049072 | 4 | 4 | 1.2585
Campbell Barracks | WA - Curtin |  | 0.00085877 | 17.1 | 7 | 1.6126
Gallipoli Barracks | QLD - Ryan |  | 0 | 0 | 0 | 0
Total |  | 212.5 | 0.0049072 | 97.1 | 40 | 18.3662
P0007 Airfield Capital Works (East Sale, Pearce, Gingin and Oakey) [1]
Army Aviation Centre Oakey | QLD - Groom |  | 0 | 11.8 | 11.8 | 1.629
RAAF East Sale | VIC - Gippsland |  | 0 | 42 | 45.7 | 2.4699
RAAF Pearce | WA - Pearce |  | 0 | 12.6 | 0 | 0
RAAF Gingin | WA - Pearce |  | 0 | 3.1 | 0 | 0
Total |  | 149 | 0 | 69.5 | 57.5 | 4.0989
Defence Terrestrial Communications Network Facilities Upgrade (JP 2047 Phase 3)[2]
National |  | 131.1 | 116.2386 | 8.5 | 13.8 | 13.2872
Defence Force School of Signals (DFSS) Redevelopment Project, Watsonia [1]
HMAS Cerberus | VIC - Flinders |  | 4.444 | 1.4 | 0.9 | 0.033352
Simpson Barracks | VIC - Jagajaga |  | 66.6596 | 15.9 | 13.5 | 0.50028
Total |  | 115.6 | 71.1036 | 17.3 | 14.4 | 0.53363
Airfield Capital Works (Curtin, Tindal and Townsville)[1]
RAAF Tindal | NT - Lingiari |  | 42.0288 | 13.2 | 7.3 | 4.2336
RAAF Curtin | WA - Durack |  | 15.2 | 0.1 | 0.1 | 0.01
RAAF Townsville | QLD - Herbert |  | 0 | 0 | 0 | 0
Total |  | 95.312 | 57.2288 | 13.3 | 7.4 | 4.2436
Space Surveillance Telescope (JP 3029 Phase 2)
Harold E Holt, Exmouth | WA - Durack | 97.2 | 47.9725 | 5.5 | 31.3 | 40.195
Russell Offices Buildings 5 and 6 Infrastructure Upgrade
Russell Offices | ACT - Canberra | 75.4 | 11.7848 | 31 | 31 | 28.7317
Delamere Range Facilities Redevelopment
Delamere Air Weapons Range | NT - Lingiari | 74.4 | 56.5006 | 11.6 | 17.1 | 16.6515
Land 17 Phase 1B/1C [1]
Proof & Experimental Establishment - Port Wakefield | QLD - Grey [5] |  | 1.2 | 0 | 0 | 0
Campbell Barracks | WA - Curtin |  | 3.6 | 0.7 | 0.6 | 1
Holsworthy Barracks | NSW - Hughes |  | 4 | 0.4 | 0.4 | 0.3
Robertson Barracks | NT - Lingiari [6] |  | 8.1 | 0.6 | 6.1 | 6.4
Lavarack Barracks | QLD - Herbert |  | 8.6 | 0 | 0.1 | 0.1
RAAF Williamtown | NSW - Paterson |  | 4.6 | 0.6 | 0.9 | 0.6
Puckapunyal Training Area | VIC - Nicholls [5] |  | 7.4 | 1 | 1.8 | 1.7
Gallipoli Barracks, Enoggera | QLD - Ryan |  | 6.7 | 0 | 0 | 0
Total |  | 57.116 | 44.18 | 3.3 | 9.9 | 10.1
Jindalee Operational Radar Networks (JORN) Phase 6 Facilities Project
Alice Springs | NT - Lingiari | 50.7 | 0.63932 | 0 | 8.6 | 0.46864
REDFIN Infrastructure (JP 2097 Phase 1B)[1]
Campbell Barracks | WA - Curtin |  | 9.5657 | 0 | 0.2 | 0.82236
Holsworthy Barracks | NSW - Hughes |  | 23.9142 | 0.1 | 0.5 | 0
Lavarack Barracks | QLD - Herbert |  | 9.5657 | 0 | 0.2 | 0
Defence Establishment Howard Springs | NT - Lingiari [5] |  | 0 | 0 | 0 | 0
Total |  | 50.479 | 43.0456 | 0.1 | 0.9 | 0.82236
Woomera Range Remediation Facilities (JP 3024 Phase 1)
Woomera | SA - Grey | 48.64 | 30.0715 | 1 | 16.3 | 13.1979
Replacement Aviation Refuelling Vehicles Infrastructure (JP 157 Ph 1) [1]
HMAS Stirling | WA - Brand |  | 0.13947 | 1.3 | 1.3 | 0.057028
RAAF Amberley | QLD - Blair |  | 0.032185 | 0.3 | 0.3 | 0.26199
RAAF Richmond | NSW - Greenway Macquarie [6] |  | 0.3755 | 3.5 | 3.5 | 0.15354
Woomera | SA - Grey |  | 0.25748 | 1.4 | 2.4 | 0.10528
Robertson Barracks | NT - Lingiari |  | 0.20384 | 1.9 | 1.9 | 0.083349
Holsworthy Barracks | NSW - Hughes |  | 0.18238 | 1.7 | 1.7 | 0.074576
RAAF Tindal | NT - Lingiari |  | 0.26821 | 2.5 | 2.5 | 0.10967
RAAF Learmonth | WA - Durack |  | 0.41841 | 4.9 | 3.9 | 0.17109
RAAF Curtin | WA - Durack |  | 0.010728 | 0.1 | 0.1 | 0.0043868
RAAF Townsville | QLD - Herbert |  | 0.66516 | 6.2 | 6.2 | 17.2798
RAAF Williamtown | NSW - Paterson |  | 0.48278 | 4.5 | 4.5 | 0.19741
RAAF Edinburgh | SA - Wakefield Spence [5] |  | 0.41841 | 3.9 | 3.9 | 0.17109
RAAF Darwin | NT - Solomon |  | 0.21457 | 2 | 2 | 0.087736
Total |  | 40.4 | 3.6691 | 34.2 | 34.2 | 18.7569
Puckapunyal Military Area High Voltage Upgrade
Puckapunyal Training Area | VIC - Nicholls [5] | 32.7 | 26.8636 | 1.3 | 3.3 | 2.8012
Electronic Warfare Operational Support (JP500 Phase 2)
RAAF Edinburgh | SA - Wakefield | 24.9 | 14.1324 | 2.4 | 5.4 | 4.7705
LAND 155 Enhanced Gap Crossing Capability[1]
Liverpool Military Area (LMA) | NSW - Hughes [6] |  | 3.5817 | 0.3 | 0.1 | 0.28006
Robertson Barracks | NT - Solomon Lingiari [6] |  | 0 | 0.5 | 0 | 0
Lavarack Barracks, Townsville | QLD - Herbert |  | 3.0272 | 0.1 | 0.5 | 0.18291
Wallangarra | QLD - Maranoa |  | 4.4975 | 0.9 | 0.1 | 0.3126
Total |  | 23.247 | 11.0866 | 1.8 | 0.7 | 0.77557
LAND 2110 Phase 1B - Chemical, Biological, Radiological, Nuclear Defence (CBRND) Capability Facilities [1]
RAAF Amberley | QLD - Blair |  | 0.093282 | 0 | 0.4 | 0.036583
HMAS Stirling | WA - Brand |  | 0.046641 | 0 | 0.2 | 0.018291
Holsworthy Barracks | NSW - Hughes |  | 0.023321 | 0 | 0.1 | 0.0091457
HMAS Cerberus | VIC - Flinders |  | 0.023321 | 0 | 0.1 | 0.0091457
Dutson Air Weapons Range | VIC - Gippsland |  | 0.023321 | 0 | 0.1 | 0.0091457
Bindnoon Training Area | WA - Pearce [5] |  | 0 | 0 | 0 | 0
Lavarack Barracks | QLD - Herbert |  | 0.069962 | 0 | 0.3 | 0.027437
Kapooka Military Area | NSW - Riverina |  | 0.069962 | 0 | 0.3 | 0.027437
RAAF Base Wagga | NSW - Riverina |  | 0.023321 | 0 | 0.1 | 0.0091457
Robertson Barracks | NT - Solomon Lingiari [6] |  | 0.16324 | 0 | 0.7 | 0.06402
RAAF Edinburgh | SA - Wakefield Spence [5] |  | 0.093282 | 0 | 0.4 | 0.036583
HMAS Creswell | ACT - Fenner |  | 0.046641 | 0 | 0.2 | 0.018291
Majura Range | ACT - Canberra |  | 0.046641 | 0 | 0.2 | 0.018291
Gallipoli Barracks | QLD - Ryan |  | 0.023321 | 0 | 0.1 | 0.0091457
Total |  | 16.7 | 0.74626 | 0 | 3.2 | 0.29266
HMAS Moreton Unit Relocation
HMAS Moreton | QLD - Griffith | 15.646 | 0.88892 | 8.9 | 12.6 | 13.1177
Projects in or about to enter Defects Liability Period[3] |  |  | 248.5261 | 5.1 | 4.8 | 2.7246
Total—all projects |  | 10338.17 | 5644.2212 | 1748.4 | 1758.8 | 1661.7793
Notes
1. These projects cross state and electoral boundaries. Cumulative expenditure to 30 June 2018, and estimated and actual expenditure for 2018-19, are provided in the table per location.
2. This project is delivering facilities at over 200 locations that cross state and electoral boundaries.
3. This amount represents the expenditure estimates for contract administration of five completed projects during their first year in use.
4. Values of $0.0m represent amounts greater than $0 but less than $50,000.
5. Change due to boundary change/renaming
6. Electorate has been incorrectly reported
7. These Projects have received a Real Cost Increase approved by Government